## Graph
[19 empty] | Hopper | [5 empty] | Pipeline/Bucket | [6 empty] | Combo - All Types
[19 empty] | Bucket | [5 empty] | Pipeline/Hopper
[19 empty] | Pipeline | [5 empty] | Hopper/Bucket
District | Project | Fiscal Year | Project Type / Mission | Project Category | Preferred Start | Duration (days) | Estimated Quantity (CY) | Disposal Type | Dredge Type | SBA Set Aside | FY18 | [12 empty] | FY19 | [12 empty] | FY20 | [11 empty] | FY21 | [11 empty] | FY22 | [11 empty] | FY23
[11 empty] | October | November | December | January | February | March | April | May |  | June | July | August | September | October |  | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September
MVK | Emergency Contract: JBJ Waterway (Red River) | 18 | NAV | O&M | 2018-03-29 | 75 | 592340 |  | Pipeline | Small Business
MVK | Consolidated: JBJ Waterway, Ouachita/Black | 18 | NAV | O&M | 2018-04-20 | 119 | 1785000 |  | Pipeline | Unrestricted
MVK | Consolidated: Lake Providence, Vicksburg, Greenville, Yellow Bend, Mouth of Yazoo, Claiborne Co, Rosedale, Yazoo R, Madison Parish | 18 | NAV | O&M | 2018-07-01 | 121 | 1815000 |  | Pipeline | Unrestricted
MVK | MATOC: JBJ, Ouachita/Black R, Rosedale, Yellow Bend, Greenville, Lake Providence, Madison Parish, Vicksburg, Mouth of Yazoo, Yazoo R, Claiborne Co. | 19 | NAV | O&M | 2019-04-01 | 268 | 4020000 |  | Pipeline | Unrestricted
MVK | MATOC: JBJ, Ouachita/Black R, Rosedale, Yellow Bend, Greenville, Lake Providence, Madison Parish, Vicksburg, Mouth of Yazoo, Yazoo R, Claiborne Co. | 20 | NAV | O&M | 2020-04-01 | 268 | 4020000 |  | Pipeline | Unrestricted
MVK | MATOC: JBJ, Ouachita/Black R, Rosedale, Yellow Bend, Greenville, Lake Providence, Madison Parish, Vicksburg, Mouth of Yazoo, Yazoo R, Claiborne Co. | 21 | NAV | O&M | 2021-04-01 | 268 | 4020000 |  | Pipeline | Unrestricted
MVK | MATOC: JBJ, Ouachita/Black R, Rosedale, Yellow Bend, Greenville, Lake Providence, Madison Parish, Vicksburg, Mouth of Yazoo, Yazoo R, Claiborne Co. | 22 | NAV | O&M | 2022-04-01 | 268 | 4020000 |  | Pipeline | Unrestricted
MVK | MATOC: JBJ, Ouachita/Black R, Rosedale, Yellow Bend, Greenville, Lake Providence, Madison Parish, Vicksburg, Mouth of Yazoo, Yazoo R, Claiborne Co. | 23 | NAV | O&M | 2023-04-01 | 268 | 4020000 |  | Pipeline | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 18 | NAV | O&M | 2018-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVM | Mississippi R Lease Dustpan | 18 | NAV | O&M | 2018-10-01 | 253 | 15200000 | Overboard and Open Water | Dustpan | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 19 | NAV | O&M | 2019-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 20 | NAV | O&M | 2020-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 21 | NAV | O&M | 2021-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 22 | NAV | O&M | 2022-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVM | SATOC: Elvis Strahr, New Madrid/Mile 889, New Madrid Co, Caruthersville, Osceola, Helena, Helena/Phillips Co, NW Tenn. Regional, Wolf R, Memphis / McKellar Lake | 23 | NAV | O&M | 2023-07-01 | 197 | 2080000 | Open and Upland | Pipeline | Unrestricted
MVN | Baptiste Collette CY | 18 | NAV | O&M | 2018-09-01 | 90 | 1500000 |  | Pipeline | Unrestricted
MVN | Bayou Lafourche CY | 18 | NAV | O&M | 2018-09-17 | 91 | 1600000 |  | Pipeline | Unrestricted
MVN | Houma Navigation Canal Bar & Bay CY | 18 | NAV | O&M | 2018-10-13 | 109 | 1800000 |  | Pipeline | Unrestricted
MVN | Calcasieu River Miles 5-17 & Devil's Elbow | 18 | NAV | O&M | 2018-11-01 | 256 | 4500000 |  | Pipeline | Unrestricted
MVN | Mermentau Little Chenier CY | 19 | NAV | O&M | 2018-11-15 | 92 | 9000 |  | Bucket | Unrestricted
MVN | Freshwater Bayou Bar CY | 19 | NAV | O&M | 2018-11-15 | 105 | 1500000 |  | Pipeline | Unrestricted
MVN | Atchafalaya River CY | 19 | NAV | O&M | 2018-12-01 | 90 | 4000000 |  | Pipeline | Unrestricted
MVN | Calcasieu Bar Channel HDR #1-18 | 19 | NAV | O&M | 2019-01-02 | 148 | 7000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #1-19 | 19 | NAV | O&M | 2019-03-01 | 92 | 3000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #2-19 | 19 | NAV | O&M | 2019-03-15 | 77 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass CDR #1-19 | 19 | NAV | O&M | 2019-03-15 | 107 | 3000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Southwest Pass HDR #3-19 | 19 | NAV | O&M | 2019-04-01 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #4-19 | 19 | NAV | O&M | 2019-04-15 | 76 | 2500000 |  | Hopper | Unrestricted
MVN | Houma Navigation Canal Inland CY | 19 | NAV | O&M | 2019-04-15 | 61 | 900000 |  | Pipeline | Unrestricted
MVN | Mississippi River New Orleans Harbor #1-19 | 19 | NAV | O&M | 2019-05-16 | 71 | 1000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Lease Dustpan Contract | 19 | NAV | O&M | 2019-07-01 | 90 | 5400000 |  | Dustpan | Unrestricted
MVN | Atchafalaya Basin, GIWW & Miscellaneous Project CDR IDIQ | 19 | NAV | O&M | 2019-07-25 | 90 | 1200000 |  | Pipeline | Unrestricted
MVN | Calcasieu River Miles 17-36 & Devil's Elbow | 19 | NAV | O&M | 2019-09-09 | 310 | 4500000 |  | Pipeline | Unrestricted
MVN | GIWW Alternate Route CY | 19 | NAV | O&M | 2019-09-21 | 122 | 700000 |  | Pipeline | Unrestricted
MVN | Atchafalaya River CDR #1-19 | 20 | NAV | O&M | 2019-12-01 | 90 | 3000000 |  | Pipeline | Unrestricted
MVN | Calcasieu Bar Channel HDR #1-19 | 20 | NAV | O&M | 2020-01-02 | 90 | 7000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #1-20 | 20 | NAV | O&M | 2020-03-01 | 120 | 3000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #2-20 | 20 | NAV | O&M | 2020-03-15 | 108 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass CDR #1-20 | 20 | NAV | O&M | 2020-03-15 | 105 | 3000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Southwest Pass HDR #3-20 | 20 | NAV | O&M | 2020-04-01 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #4-20 | 20 | NAV | O&M | 2020-04-15 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River New Orleans Harbor CDR #1-20 | 20 | NAV | O&M | 2020-05-16 | 60 | 1000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Lease Dustpan Contract | 20 | NAV | O&M | 2020-07-01 | 90 | 5400000 |  | Dustpan | Unrestricted
MVN | Atchafalaya Basin, GIWW & Miscellaneous Project CDR IDIQ | 20 | NAV | O&M | 2020-07-25 | 90 | 1200000 |  | Pipeline | Unrestricted
MVN | Calcasieu River Miles 5-17 & Devil's Elbow | 20 | NAV | O&M | 2020-09-21 | 310 | 4500000 |  | Pipeline | Unrestricted
MVN | Miss. River New Orleans Harbor & Various Bar Channels CDR #3-20 | 20 | NAV | O&M | 2020-09-24 | 60 | 700000 |  | Pipeline | Unrestricted
MVN | Atchafalaya River CDR #1-21 | 21 | NAV | O&M | 2020-12-01 | 90 | 3000000 |  | Pipeline | Unrestricted
MVN | Calcasieu Bar Channel HDR #1-20 | 21 | NAV | O&M | 2021-01-02 | 90 | 7000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #1-21 | 21 | NAV | O&M | 2021-03-01 | 120 | 3000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #2-21 | 21 | NAV | O&M | 2021-03-15 | 108 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass CDR #1-21 | 21 | NAV | O&M | 2021-03-15 | 105 | 3000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Southwest Pass HDR #3-21 | 21 | NAV | O&M | 2021-04-01 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #4-21 | 21 | NAV | O&M | 2021-04-15 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River New Orleans Harbor CDR #1-21 | 21 | NAV | O&M | 2021-05-16 | 60 | 1000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Lease Dustpan Contract | 21 | NAV | O&M | 2021-07-01 | 90 | 5400000 |  | Dustpan | Unrestricted
MVN | Atchafalaya Basin, GIWW & Miscellaneous Project CDR IDIQ | 21 | NAV | O&M | 2021-07-25 | 90 | 1200000 |  | Pipeline | Unrestricted
MVN | Calcasieu River Miles 17-36 & Devil's Elbow | 21 | NAV | O&M | 2021-09-21 | 310 | 4500000 |  | Pipeline | Unrestricted
MVN | Miss. River New Orleans Harbor & Various Bar Channels CDR #3-21 | 21 | NAV | O&M | 2021-09-24 | 60 | 700000 |  | Pipeline | Unrestricted
MVN | Atchafalaya River CDR #2-21 | 22 | NAV | O&M | 2021-12-01 | 90 | 3000000 |  | Pipeline | Unrestricted
MVN | Calcasieu Bar Channel HDR #1-21 | 22 | NAV | O&M | 2022-01-02 | 90 | 7000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #1-22 | 22 | NAV | O&M | 2022-03-01 | 120 | 3000000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #2-22 | 22 | NAV | O&M | 2022-03-15 | 108 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass CDR #1-22 | 22 | NAV | O&M | 2022-03-15 | 105 | 3000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Southwest Pass HDR #3-22 | 22 | NAV | O&M | 2022-04-01 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River Southwest Pass HDR #4-22 | 22 | NAV | O&M | 2022-04-15 | 75 | 2500000 |  | Hopper | Unrestricted
MVN | Mississippi River New Orleans Harbor CDR #1-22 | 22 | NAV | O&M | 2022-05-16 | 60 | 1000000 |  | Pipeline | Unrestricted
MVN | Mississippi River Lease Dustpan Contract | 22 | NAV | O&M | 2022-07-01 | 90 | 5400000 |  | Dustpan | Unrestricted
MVN | Atchafalaya Basin, GIWW & Miscellaneous Project CDR IDIQ | 22 | NAV | O&M | 2022-07-25 | 90 | 1200000 |  | Pipeline | Unrestricted
MVN | Calcasieu River Miles 5-17 & Devil's Elbow | 22 | NAV | O&M | 2022-09-21 | 310 | 4500000 |  | Pipeline | Unrestricted
MVN | Miss. River New Orleans Harbor & Various Bar Channels CDR #3-22 | 22 | NAV | O&M | 2022-09-24 | 60 | 700000 |  | Pipeline | Unrestricted
MVP | Corps Island Unloading, UMR Mile 799.2 | 18 | NAV | O&M | 2019-04-01 | 244 | 500000 |  | Pipeline.Bucket | Unrestricted
MVP | Pool 2 Channel Modification, UMR Mile 819.0 | 19 | NAV | O&M | 2019-05-01 | 214 | 400000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 1 Channel | 19 | NAV | O&M | 2019-05-15 | 175 | 250000 |  | Bucket | Small Business
MVP | McGregor Lake HREP, UMR Mile 634.0 | 19 | NAV | New Work | 2019-05-15 | 570 | 350000 |  | Pipeline.Bucket | Unrestricted
MVP | O&M Island Above Lock and Dam 2, UMR Mile 815.5 | 19 | NAV | O&M | 2019-06-01 | 395 | 325000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 2 Unload | 19 | NAV | O&M | 2019-07-01 | 140 | 150000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 1 Channel | 20 | NAV | O&M | 2020-05-15 | 175 | 250000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 2 Unload | 20 | NAV | O&M | 2020-07-01 | 140 | 150000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 1 Channel | 21 | NAV | O&M | 2021-05-15 | 175 | 250000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 2 Unload | 21 | NAV | O&M | 2021-07-01 | 140 | 150000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 1 Channel | 22 | NAV | O&M | 2022-05-15 | 175 | 250000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 2 Unload | 22 | NAV | O&M | 2022-07-01 | 140 | 150000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 1 Channel | 23 | NAV | O&M | 2023-05-15 | 175 | 250000 |  | Bucket | Small Business
MVP | UMR 9-Foot Channel, Miles 857.6-614.0 Contract 2 Unload | 23 | NAV | O&M | 2023-07-01 | 140 | 150000 |  | Bucket | Small Business
MVR | Illinois Waterway | 18 | NAV | O&M | 2018-09-15 | 45 | 200000 |  | Pipeline | Small Business
MVR | Illinois Waterway | 19 | NAV | O&M | 2019-09-15 | 45 | 200000 |  | Pipeline | Small Business
MVR | Illinois Waterway | 20 | NAV | O&M | 2020-09-15 | 45 | 200000 |  | Pipeline | Small Business
MVR | Illinois Waterway | 21 | NAV | O&M | 2021-09-15 | 45 | 200000 |  | Pipeline | Small Business
MVR | Illinois Waterway | 22 | NAV | O&M | 2022-09-15 | 45 | 200000 |  | Pipeline | Small Business
MVS | Southeast Missouri Port (Mile 48 UMR) | 18 | NAV | O&M | 2018-09-01 | 4 | 60000 |  | Pipeline | Unrestricted
MVS | Southeast Missouri Port (Mile 48 UMR) | 19 | NAV | O&M | 2019-09-01 | 4 | 60000 |  | Pipeline | Unrestricted
MVS | Southeast Missouri Port (Mile 48 UMR) | 20 | NAV | O&M | 2020-09-01 | 4 | 60000 |  | Pipeline | Unrestricted
MVS | Southeast Missouri Port (Mile 48 UMR) | 21 | NAV | O&M | 2021-09-01 | 4 | 60000 |  | Pipeline | Unrestricted
MVS | Southeast Missouri Port (Mile 48 UMR) | 22 | NAV | O&M | 2022-09-01 | 4 | 60000 |  | Pipeline | Unrestricted
NAB | Rhodes Point (Sheep Pen Gut) | 18 | NAV | New Work | 2018-10-15 | 30 | 20000 |  | Pipeline | Small Business
NAB | Twitch Cove & Big Thorofare | 18 | NAV | O&M | 2018-10-15 | 120 | 90000 |  | Pipeline | Small Business
NAB | Baltimore Harbor & Channels (MD) | 19 | NAV | O&M | 2018-12-01 | 220 | 1900000 |  | Bucket | Unrestricted
NAB | Wicomico River (Upper) | 19 | NAV | O&M | 2018-12-01 | 160 | 100000 |  | Pipeline | Small Business
NAB | Baltimore Harbor & Channels (VA - York Spit) | 19 | NAV | O&M | 2019-04-01 | 220 | 2500000 |  | Bucket | Unrestricted
NAB | Baltimore Harbor & Channels (MD) | 20 | NAV | O&M | 2019-12-01 | 220 | 2000000 |  | Bucket | Unrestricted
NAB | Herring Bay & Rockhold Creek | 20 | NAV | O&M | 2019-12-01 | 45 | 40000 |  | Pipeline | Small Business
NAB | Wicomico River (Lower) | 20 | NAV | O&M | 2019-12-01 | 160 | 100,00 |  | Pipeline | Small Business
NAB | Fishing Creek | 20 | NAV | O&M | 2020-02-01 | 45 | 40000 |  | Pipeline | Small Business
NAB | Baltimore Harbor & Channels (MD) | 21 | NAV | O&M | 2020-12-01 | 220 | 2000000 |  | Bucket | Unrestricted
NAB | Wicomico River (Upper) | 21 | NAV | O&M | 2020-12-01 | 160 | 100000 |  | Pipeline | Small Business
NAB | Chester River (Kent Narrows) | 21 | NAV | O&M | 2021-01-01 | 60 | 45000 |  | Pipeline | Small Business
NAB | Atlantic Coast of MD / Ocean City Beach Re-nourishment | 22 | FRM | O&M | 2021-10-01 | 180 | 800000 |  | Hopper | Unrestricted
NAB | Baltimore Harbor & Channels (MD) | 22 | NAV | O&M | 2021-12-01 | 220 | 1500000 |  | Bucket | Unrestricted
NAB | Baltimore Harbor & Channels (VA - Cape Henry) | 22 | NAV | O&M | 2021-12-01 | 220 | 1500000 |  | Hopper | Unrestricted
NAB | Wicomico River (Lower) | 22 | NAV | O&M | 2021-12-01 | 160 | 100000 |  | Pipeline | Small Business
NAB | Honga River & Tar Bay | 22 | NAV | O&M | 2022-01-01 | 180 | 300000 |  | Pipeline | Small Business
NAB | Baltimore Harbor & Channels (MD) | 23 | NAV | O&M | 2022-12-01 | 220 | 1500000 |  | Bucket | Unrestricted
NAB | Wicomico River (Lower) | 23 | NAV | O&M | 2022-12-01 | 160 | 100000 |  | Pipeline | Small Business
NAB | Baltimore Harbor & Channels (VA - York Spit) | 23 | NAV | O&M | 2023-04-01 | 220 | 1500000 |  | Bucket | Unrestricted
NAE | Boston Harbor, MA | 18 | NAV | New Work | 2018-07-09 | 730 | 11620000 |  | Bucket | Unrestricted
NAE | Plymouth Harbor, MA | 19 | NAV | O&M | 2018-10-01 | 120 | 384000 |  | Bucket | Unrestricted
NAE | Saco River, ME | 19 | NAV | O&M | 2018-11-01 | 120 | 140000 |  | Pipeline | Unrestricted
NAE | Annisquam River, MA | 20 | NAV | O&M | 2019-10-01 | 150 | 160000 |  | Bucket | Small Business
NAE | Green Harbor, MA | 20 | NAV | O&M | 2019-10-01 | 90 | 100000 |  | Bucket | Small Business
NAE | Wellfleet Harbor, MA | 20 | NAV | O&M | 2019-10-01 | 120 | 190000 |  | Bucket | Unrestricted
NAE | Hampton Harbor, NH | 20 | NAV | O&M | 2019-10-01 | 120 | 175000 |  | Pipeline | Small Business
NAE | Portsmouth Harbor | 20 | NAV | New Work | 2019-10-31 | 180 | 755000 |  | Bucket | Unrestricted
NAE | Cape Porpoise, Kennebunkport, ME | 20 | NAV | O&M | 2019-11-01 | 120 | 35000 |  | Bucket | Small Business
NAE | Wood Island/Biddeford Pool, ME | 20 | NAV | O&M | 2019-11-01 | 60 | 40000 |  | Bucket | Small Business
NAE | Kennebec River, ME | 20 | NAV | O&M | 2019-12-15 | 14 | 70000 |  | Hopper | Unrestricted
NAE | Point Judith Harbor, RI | 20 | NAV | New Work | 2020-09-01 | 40 | 24000 |  | Bucket | Small Business
NAE | Stony Creek, CT | 21 | NAV | O&M | 2020-10-01 | 75 | 50000 |  | Bucket | Small Business
NAE | Blue Hill Harbor, ME | 21 | NAV | New Work | 2020-11-01 | 90 | 60000 |  | Bucket | Small Business
NAE | Milford Harbor, CT | 21 | NAV | O&M | 2021-09-15 | 90 | 70000 |  | Bucket | Small Business
NAE | New Haven Harbor, CT | 22 | NAV | New Work | 2021-10-01 | 365 | 4500000 |  | Bucket | Unrestricted
NAE | New Haven Hbr (Maint for improvement), CT | 22 | NAV | O&M | 2021-10-01 | 60 | 300000 |  | Bucket | Unrestricted
NAE | West River, CT | 22 | NAV | O&M | 2021-10-01 | 90 | 120000 |  | Bucket | Unrestricted
NAE | Weymouth Fore River, MA | 22 | NAV | O&M | 2021-10-01 | 120 | 600000 |  | Bucket | Unrestricted
NAE | Scarborough River, ME | 22 | NAV | O&M | 2021-10-01 | 90 | 100000 |  | Pipeline | Small Business
NAE | Westcott Cove, CT | 22 | NAV | O&M | 2021-10-01 | 75 | 40000 |  | Pipeline | Small Business
NAE | Boston Harbor, MA | 22 | NAV | New Work | 2021-11-01 | 365 | 380000 |  | Bucket | Unrestricted
NAE | Essex River, MA | 22 | NAV | O&M | 2021-11-01 | 90 | 70000 |  | Bucket | Small Business
NAE | Great Chebeague Island, ME | 22 | NAV | New Work | 2021-11-01 | 45 | 32000 |  | Bucket | Small Business
NAE | Rye Harbor, NH | 22 | NAV | O&M | 2021-11-01 | 60 | 50000 |  | Bucket | Small Business
NAE | Newburyport Harbor, MA | 22 | NAV | O&M | 2022-07-01 | 45 | 200000 |  | Hopper | Unrestricted
NAE | Greenwich Harbor, CT | 23 | NAV | O&M | 2022-10-01 | 150 | 120000 |  | Bucket | Unrestricted
NAE | New Bedford Harbor, MA | 23 | NAV | O&M | 2022-10-01 | 180 | 1000000 |  | Bucket | Unrestricted
NAE | Providence River, RI | 23 | NAV | O&M | 2022-10-01 | 180 | 900000 |  | Bucket | Unrestricted
NAE | Westport Harbor, CT | 23 | NAV | O&M | 2022-10-01 | 45 | 25000 |  | Bucket | Small Business
NAE | CT River Entrance, CT | 23 | NAV | O&M | 2022-10-01 | 120 | 150000 |  | Pipeline.Hopper | Unrestricted
NAE | Frechboro, ME | 23 | NAV | O&M | 2022-11-01 | 60 | 20000 |  | Bucket | Small Business
NAE | Searsport Harbor, ME | 23 | NAV | O&M | 2022-11-01 | 90 | 40000 |  | Bucket | Small Business
NAE | Union River, ME | 23 | NAV | O&M | 2022-11-01 | 30 | 30000 |  | Bucket | Small Business
NAE | Town River, MA | 23 | NAV | O&M | 2022-11-15 | 120 | 120000 |  | Bucket | Small Business
NAE | Wareham River, MA | 23 | NAV | O&M | 2023-09-01 | 60 | 60000 |  | Pipeline | Small Business
NAN | Newark Bay, NJ Maintenance | 18 | NAV | O&M | 2018-07-05 | 90 | 190000 |  | Bucket | Unrestricted
NAN | Long Beach, NY Contract 2 | 18 | NAV | New Work | 2018-07-10 | 479 | 4800000 |  | Pipeline | Unrestricted
NAN | Moriches Inlet, NY Maintenance | 18 | NAV | O&M | 2018-07-31 | 50 | 160000 |  | Pipeline | Unrestricted
NAN | NY/NJ Channels - Ward Point Maintenance Dredging | 18 | NAV | O&M | 2018-08-27 | 35 | 183000 |  | Bucket | Unrestricted
NAN | Hudson River Maintenance | 18 | NAV | O&M | 2018-09-01 | 60 | 200000 |  | Hopper | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 18 | NAV | O&M | 2018-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAN | Fire Island Inlet and Shores Westerly to Jones Inlet Beach Erosion Control & Navigation Project, NY | 18 | FRM | O&M | 2018-10-01 | 190 | 1800000 |  | Pipeline | Unrestricted
NAN | Long Island Intracoastal Waterway, NY Maintenance | 18 | NAV | O&M | 2018-10-01 | 110 | 110000 |  | Pipeline | Unrestricted
NAN | Lake Montauk Harbor, NY Maintenance | 18 | NAV | O&M | 2018-10-06 | 35 | 40000 |  | Pipeline | Unrestricted
NAN | Fire Island Inlet to Montauk Point (FIMP), NY (Fire Island Communities 3B2; Ocean Bay Park to Davis Park) | 19 | FRM | New Work | 2018-11-15 | 365 | 2000000 |  | Hopper | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 19 | NAV | O&M | 2019-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAN | Union Beach, NJ Contract 1 | 20 | FRM | New Work | 2020-07-31 | 180 | 700000 |  | Hopper | Unrestricted
NAN | Hudson River Maintenance | 20 | NAV | O&M | 2020-09-01 | 60 | 200000 |  | Hopper | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 20 | NAV | O&M | 2020-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 21 | NAV | O&M | 2021-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAN | Hudson River Maintenance | 22 | NAV | O&M | 2022-09-01 | 70 | 225000 |  | Hopper | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 22 | NAV | O&M | 2022-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAN | NY Harbor - Sandy Hook Channel Maintenance | 23 | NAV | O&M | 2023-09-16 | 60 | 200000 |  | Bucket | Unrestricted
NAO | James River | 18 | NAV | O&M | 2017-06-15 | 245 | 1000000 |  | Bucket | Small Business
NAO | Norfolk Harbor and Channels, Craney Island Expansion, VA | 18 | NAV | New Work | 2018-02-23 | 112 | 325000 |  | Pipeline.Bucket | Unrestricted
NAO | Norfolk Harbor and Channels, Craney Island Expansion, VA | 19 | NAV | New Work | 2018-03-01 | 90 | 150000 |  | Pipeline | Unrestricted
NAO | James River | 19 | NAV | O&M | 2018-06-15 | 245 | 1000000 |  | Pipeline | Small Business
NAO | AIWW-DSC | 18 | FRM | O&M | 2018-07-27 | 32 | 25000 |  | Pipeline | Small Business
NAO | Queens Creek | 19 | NAV | O&M | 2018-10-01 | 75 | 20000 |  | Pipeline | Small Business
NAO | Back River Langley AFB | 19 | NAV | New Work | 2018-10-26 | 315 | 150000 |  | Bucket | Unrestricted
NAO | Thimble Shoal Channel | 19 | NAV | O&M | 2018-11-15 | 225 | 1600000 |  | Hopper | Unrestricted
NAO | Lynnhaven Inlet | 19 | NAV | O&M | 2018-12-01 | 145 | 190000 |  | Pipeline | Small Business
NAO | Chincoteague Bay Greenbackville | 19 | NAV | O&M | 2019-01-01 | 75 | 15000 |  | Pipeline | Small Business
NAO | Norfolk Harbor, Sewells Point to Lamberts Bend | 19 | NAV | O&M | 2019-01-15 | 120 | 500000 |  | Pipeline | Unrestricted
NAO | Rudee Inlet | 19 | NAV | O&M | 2019-02-01 | 90 | 200000 |  | Pipeline | Unrestricted
NAO | Sandbridge Beach, VA | 19 | FRM | New Work | 2019-03-15 | 180 | 1800000 |  | Hopper | Unrestricted
NAO | Virginia Beach Hurricane Protection, Virginia Beach, VA | 19 | FRM | New Work | 2019-05-01 | 120 | 1200000 |  | Hopper | Unrestricted
NAO | Oyster Channel | 19 | NAV | O&M | 2019-05-01 | 60 | 60000 |  | Pipeline | Small Business
NAO | Norfolk Harbor, Channel to Newport News | 19 | NAV | O&M | 2019-05-15 | 60 | 150000 |  | Pipeline | Unrestricted
NAO | James River | 20 | NAV | O&M | 2019-06-15 | 240 | 1000000 |  | Pipeline | Small Business
NAO | Norfolk Harbor and Channels Deepening, VA (55-Foot Deepening) | 20 | NAV | New Work | 2019-10-01 | 365 | 650000 |  | Hopper | Unrestricted
NAO | Atlantic Ocean Channel | 20 | NAV | O&M | 2019-11-15 | 120 | 250000 |  | Hopper | Unrestricted
NAO | Tangier Channel | 20 | NAV | O&M | 2019-12-01 | 75 | 35000 |  | Pipeline | Small Business
NAO | Wachapreague | 20 | NAV | O&M | 2019-12-01 | 45 | 50000 |  | Pipeline | Small Business
NAO | Norfolk Harbor, Sewells Point to Lamberts Bend | 20 | NAV | O&M | 2020-01-01 | 120 | 600000 |  | Pipeline | Unrestricted
NAO | Bradford Bay | 20 | NAV | O&M | 2020-01-15 | 75 | 100000 |  | Pipeline | Small Business
NAO | Milford Haven | 20 | NAV | O&M | 2020-02-01 | 75 | 25000 |  | Pipeline | Small Business
NAO | Norfolk Harbor and Channels Deepening, VA (55-Foot Deepening) | 21 | NAV | New Work | 2020-10-01 | 365 | 2750000 |  | Hopper | Unrestricted
NAO | Norfolk Harbor Craney Island Rehandling Basin | 21 | NAV | O&M | 2020-12-01 | 150 | 1500000 |  | Pipeline | Unrestricted
NAO | Tylers Beach | 21 | NAV | O&M | 2020-12-01 | 60 | 20000 |  | Pipeline | Small Business
NAO | Norfolk Harbor Southern Branch Deepening, VA | 21 | NAV | New Work | 2021-01-01 | 270 | 725000 |  | Pipeline | Unrestricted
NAO | Norfolk Harbor, Sewells Point to Lamberts Bend | 21 | NAV | O&M | 2021-01-01 | 120 | 500000 |  | Pipeline | Unrestricted
NAO | Water on the Coast of Virginia (WCV) | 21 | NAV | O&M | 2021-01-15 | 75 | 100000 |  | Pipeline | Small Business
NAO | Quinby Creek | 21 | NAV | O&M | 2021-02-01 | 75 | 100000 |  | Pipeline | Small Business
NAO | Southern Branch of Elizabeth River | 21 | NAV | O&M | 2021-06-01 | 90 | 200000 |  | Bucket | Unrestricted
NAO | James River | 21 | NAV | O&M | 2021-06-15 | 240 | 1000000 |  | Pipeline | Small Business
NAO | Norfolk Harbor and Channels Deepening, VA (55-Foot Deepening) | 22 | NAV | New Work | 2021-10-01 | 365 | 2750000 |  | Hopper | Unrestricted
NAO | Norfolk Harbor Southern Branch Deepening, VA | 22 | NAV | New Work | 2021-10-01 | 305 | 725000 |  | Pipeline | Unrestricted
NAO | Thimble Shoal Channel | 22 | NAV | O&M | 2021-11-15 | 180 | 500000 |  | Hopper | Unrestricted
NAO | York River Entrance | 22 | NAV | O&M | 2021-11-15 | 45 | 250000 |  | Hopper | Unrestricted
NAO | Norfolk Harbor, Sewells Point to Lamberts Bend | 22 | NAV | O&M | 2022-01-01 | 120 | 500000 |  | Pipeline | Unrestricted
NAO | Norfolk Harbor, Channel to Newport News | 22 | NAV | O&M | 2022-05-15 | 60 | 150000 |  | Pipeline | Unrestricted
NAO | James River | 23 | NAV | O&M | 2022-06-15 | 240 | 1000000 |  | Pipeline | Small Business
NAO | James River | 22 | NAV | O&M | 2022-06-15 | 245 | 1000000 |  | Pipeline | Small Business
NAO | Norfolk Harbor and Channels Deepening, VA (55-Foot Deepening) | 23 | NAV | New Work | 2022-10-01 | 365 | 1875000 |  | Hopper | Unrestricted
NAO | Queens Creek | 23 | NAV | O&M | 2022-10-01 | 75 | 20000 |  | Pipeline | Small Business
NAO | Starlings Creek | 23 | NAV | O&M | 2022-11-01 | 120 | 40000 |  | Pipeline | Small Business
NAO | Norfolk Harbor, Sewells Point to Lamberts Bend | 23 | NAV | O&M | 2023-01-01 | 120 | 500000 |  | Pipeline | Unrestricted
NAO | Water on the Coast of Virginia (WCV) | 23 | NAV | O&M | 2023-01-15 | 75 | 100000 |  | Pipeline | Small Business
NAO | Lynnhaven Inlet | 23 | NAV | O&M | 2023-02-01 | 120 | 150000 |  | Pipeline | Unrestricted
NAO | Rudee Inlet | 23 | NAV | O&M | 2023-02-01 | 90 | 200000 |  | Pipeline | Unrestricted
NAO | Oyster Channel | 23 | NAV | O&M | 2023-06-01 | 90 | 50000 |  | Pipeline | Small Business
NAP | Christina River, Wilmington Harbor | 18 | NAV | O&M | 2018-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Delaware River, Phila to Sea | 18 | NAV | O&M | 2018-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NAP | Upper Chesapeake Bay/C&D Canal | 18 | NAV | O&M | 2018-10-01 | 90 | 700000 |  | Bucket | Unrestricted
NAP | Cape May Inlet to Lower Twp (Cape May City Beachfill) | 19 | FRM | O&M | 2018-10-01 | 40 | 500000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Great Egg Harbor Inlet to Townsends Inlet, NJ | 19 | FRM | O&M | 2019-01-01 | 80 | 1000000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Townsends Inlet to Cape May Inlet (Beachfill 7-Mile Island) | 19 | FRM | O&M | 2019-02-15 | 80 | 1000000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Christina River, Wilmington Harbor | 19 | NAV | O&M | 2019-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Rehoboth/Dewey | 19 | FRM | O&M | 2019-09-01 | 60 | 600000 | Beach Nourishment | Hopper | Unrestricted
NAP | Delaware River, Phila to Sea | 19 | NAV | O&M | 2019-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NAP | Upper Chesapeake Bay/C&D Canal | 19 | NAV | O&M | 2019-10-01 | 90 | 500000 |  | Bucket | Unrestricted
NAP | Delaware River, Phila to Trenton | 19 | NAV | O&M | 2019-10-01 | 90 | 700000 |  | Pipeline | Unrestricted
NAP | Cape May Inlet to Lower Twp (Cape May City Beachfill) | 20 | FRM | O&M | 2019-10-01 | 40 | 500000 | Beach Nourishment | Pipeline.Hopper | Unrestricted
NAP | Lower Cape May Meadows - Cape May Point Environmental Restoration | 20 | FRM | O&M | 2019-11-01 | 25 | 300000 | Beach Nourishment | Hopper | Unrestricted
NAP | Great Egg Harbor Inlet - Peck Beach (Ocean City Beachfill) | 20 | FRM | O&M | 2019-12-01 | 120 | 1500000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Brigantine Inlet to Great Egg Harbor Inlet, Absecon Island | 20 | FRM | O&M | 2020-01-01 | 180 | 2000000 | Beach Nourishment | Pipeline.Hopper | Unrestricted
NAP | Bethany/South Bethany | 20 | FRM | O&M | 2020-06-01 | 50 | 500000 | Beach Nourishment | Hopper | Unrestricted
NAP | Christina River, Wilmington Harbor | 20 | NAV | O&M | 2020-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Delaware River, Phila to Sea | 20 | NAV | O&M | 2020-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NAP | Upper Chesapeake Bay/C&D Canal | 20 | NAV | O&M | 2020-10-01 | 90 | 700000 |  | Bucket | Unrestricted
NAP | Christina River, Wilmington Harbor | 21 | NAV | O&M | 2021-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Fenwick Island | 21 | FRM | O&M | 2021-07-05 | 30 | 300000 | Beach Nourishment | Hopper | Unrestricted
NAP | Broadkill Beach, DE | 21 | FRM | O&M | 2021-09-01 | 50 | 500000 | Beach Nourishment | Hopper | Unrestricted
NAP | Delaware River, Phila to Sea | 21 | NAV | O&M | 2021-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NAP | Upper Chesapeake Bay/C&D Canal | 21 | NAV | O&M | 2021-10-01 | 90 | 500000 |  | Bucket | Unrestricted
NAP | Cape May Inlet to Lower Twp (Cape May City Beachfill) | 22 | FRM | O&M | 2021-10-01 | 40 | 500000 | Beach Nourishment | Pipeline.Hopper | Unrestricted
NAP | Oakwood Beach, NJ (Renourishment) | 22 | FRM | O&M | 2021-11-01 | 20 | 150000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Great Egg Harbor Inlet to Townsends Inlet, NJ | 22 | FRM | O&M | 2022-01-01 | 80 | 1000000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Townsends Inlet to Cape May Inlet (Beachfill 7-Mile Island) | 22 | FRM | O&M | 2022-02-15 | 80 | 1000000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Christina River, Wilmington Harbor | 22 | NAV | O&M | 2022-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Manasquan Inlet to Barnegat Inlet, NJ | 22 | FRM | O&M | 2022-08-01 | 240 | 3000000 | Beach Nourishment | Pipeline.Hopper | Unrestricted
NAP | Rehoboth/Dewey | 22 | FRM | O&M | 2022-09-01 | 60 | 600000 | Beach Nourishment | Hopper | Unrestricted
NAP | Delaware River, Phila to Sea | 22 | NAV | O&M | 2022-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NAP | Upper Chesapeake Bay/C&D Canal | 22 | NAV | O&M | 2022-10-01 | 90 | 500000 |  | Bucket | Unrestricted
NAP | Delaware River, Phila to Trenton | 22 | NAV | O&M | 2022-10-01 | 90 | 1500000 |  | Pipeline | Unrestricted
NAP | Great Egg Harbor Inlet - Peck Beach (Ocean City Beachfill) | 23 | FRM | O&M | 2022-12-01 | 120 | 1500000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Brigantine Inlet to Great Egg Harbor Inlet, Brigantine Island | 23 | FRM | O&M | 2023-01-01 | 60 | 800000 | Beach Nourishment | Pipeline | Unrestricted
NAP | Brigantine Inlet to Great Egg Harbor Inlet, Absecon Island | 23 | FRM | O&M | 2023-03-01 | 180 | 2000000 | Beach Nourishment | Pipeline.Hopper | Unrestricted
NAP | Bethany/South Bethany | 23 | FRM | O&M | 2023-06-01 | 50 | 500000 | Beach Nourishment | Hopper | Unrestricted
NAP | Christina River, Wilmington Harbor | 23 | NAV | O&M | 2023-07-01 | 40 | 400000 |  | Pipeline | Unrestricted
NAP | Delaware River, Phila to Sea | 23 | NAV | O&M | 2023-09-15 | 100 | 2000000 |  | Pipeline | Unrestricted
NWP | Regional Hopper Contract (Humboldt, SF Main Ship, CLW, MCR) | 18 | NAV | O&M | 2018-05-15 | 205 | 5000000 |  | Hopper | Unrestricted
NWP | Regional Hopper Contract (Grays Harbor, Humboldt, SF Main Ship, CLW, MCR) | 19 | NAV | O&M | 2019-04-01 | 245 | 5900000 |  | Hopper | Unrestricted
NWP | Coos Bay RM12-13 Clamshell Contract | 19 | NAV | O&M | 2019-07-01 | 45 | 400000 |  | Bucket | Small Business
NWP | Oregon Clamshell (Charleston, Chinook, Port Orford, Baker Bay, CLW Side Channels) | 19 | NAV | O&M | 2019-07-01 | 105 | 253000 |  | Bucket | Small Business
NWP | Oregon Pipeline (Depoe Bay, Tillamook/Garibaldi Boat Basin) | 19 | NAV | O&M | 2019-07-15 | 75 | 45000 |  | Pipeline | Small Business
NWP | Regional Hopper Contract (Humboldt, SF Main Ship, CLW, MCR) | 20 | NAV | O&M | 2020-05-15 | 205 | 5000000 |  | Hopper | Unrestricted
NWP | Oregon Clamshell 1 (Chetco, Port Orford, Rogue River, Winchester Bay) | 20 | NAV | O&M | 2020-06-01 | 35 | 203000 |  | Bucket | Small Business
NWP | Oregon Clamshell 2 (Baker Bay, Florence Turning Basin, CLW Side Channels, Charleston) | 20 | NAV | O&M | 2020-06-15 | 95 | 240000 |  | Bucket | Small Business
NWP | Coos Bay Log Spiral Bay Pipeline Contract | 20 | NAV | O&M | 2020-08-15 | 10 | 250000 |  | Pipeline | Unrestricted
NWP | Oregon Pipeline (Bandon Boat Basin) | 20 | NAV | O&M | 2020-09-15 | 15 | 10000 |  | Pipeline | Small Business
NWP | Regional Hopper Contract (Humboldt, SF Main Ship, CLW, MCR) | 21 | NAV | O&M | 2021-05-15 | 205 | 5000000 |  | Hopper | Unrestricted
NWP | Oregon Clamshell (Port Orford, Yaquina Bay Depot Slough) | 21 | NAV | O&M | 2021-07-01 | 40 | 78000 |  | Bucket | Small Business
NWP | Oregon Clamshell (Chinook, Baker Bay, CLW Side Channels) | 21 | NAV | O&M | 2021-08-01 | 75 | 200000 |  | Bucket | Small Business
NWP | Regional Hopper Contract (Humboldt, SF Main Ship, CLW, MCR) | 22 | NAV | O&M | 2022-05-15 | 205 | 5000000 |  | Hopper | Unrestricted
NWP | Coos Bay RM 12-15 Clamshell Contract | 22 | NAV | O&M | 2022-07-01 | 70 | 1000000 |  | Bucket | Small Business
NWP | Oregon Clamshell (Chetco, Port Orford, Baker Bay, Rogue River, Florence Turning Basin, Winchester Bay, CLW Side Channels) | 22 | NAV | O&M | 2022-07-01 | 85 | 290000 |  | Bucket | Small Business
NWP | Oregon Pipeline (Yaquina Bay South Beach Marina) | 22 | NAV | O&M | 2022-07-01 | 30 | 25000 |  | Pipeline.Bucket | Small Business
NWP | Regional Hopper Contract (Humboldt, SF Main Ship, CLW, MCR) | 23 | NAV | O&M | 2023-05-15 | 205 | 5000000 |  | Hopper | Unrestricted
NWP | Oregon Clamshell (Chinook, Baker Bay, Port Orford, CLW Side Channels) | 23 | NAV | O&M | 2023-07-01 | 85 | 220000 |  | Bucket | Small Business
NWS | FY18 Westhaven Marina Maint Dredging | 18 | NAV | O&M | 2018-08-01 | 30 | 35000 |  | Bucket | Small Business
NWS | FY18 Swinomish Channel Maint Dredging | 18 | NAV | O&M | 2018-09-01 | 45 | 154000 |  | Bucket | Small Business
NWS | FY18 Snohomish River Maint Dredging | 19 | NAV | O&M | 2018-10-16 | 45 | 150000 |  | Bucket | Small Business
NWS | FY18 Grays Harbor Inner Harbor Maint Dredging | 19 | NAV | O&M | 2018-12-01 | 75 | 600000 |  | Bucket | Small Business
NWS | FY19 Grays Harbor Inner Harbor Maint Dredging | 19 | NAV | O&M | 2019-07-15 | 180 | 800000 |  | Bucket | Small Business
NWS | FY19 Bellingham - Squalicum Maint Dredging | 19 | NAV | O&M | 2019-09-01 | 50 | 351000 |  | Bucket | Small Business
NWS | FY19 Quillayute River Maint Dredging | 19 | NAV | O&M | 2019-09-01 | 20 | 60000 |  | Pipeline | Small Business
NWS | FY19 Snohomish River Maint Dredging | 20 | NAV | O&M | 2019-10-16 | 45 | 150000 |  | Pipeline | Small Business
NWS | FY19 Duwamish Waterway Maint Dredging | 20 | NAV | O&M | 2019-12-01 | 40 | 180000 |  | Bucket | Small Business
NWS | FY20 Grays Harbor Inner Harbor Maint Dredging | 20 | NAV | O&M | 2020-07-15 | 180 | 800000 |  | Bucket | Small Business
NWS | FY20 Kenmore Maint Dredging | 20 | NAV | O&M | 2020-07-15 | 10 | 30000 |  | Bucket | Small Business
NWS | FY20 Willapa Harbor Maint Dredging | 20 | NAV | O&M | 2020-07-15 | 45 | 150000 |  | Bucket | Small Business
NWS | FY20 Snohomish River Maint Dredging | 21 | NAV | O&M | 2020-10-16 | 45 | 150000 |  | Bucket | Small Business
NWS | FY21 Grays Harbor Inner Harbor Maint Dredging | 21 | NAV | O&M | 2021-07-15 | 180 | 800000 |  | Bucket | Small Business
NWS | FY21 Quillayute River Maint Dredging | 21 | NAV | O&M | 2021-09-01 | 30 | 90000 |  | Pipeline | Small Business
NWS | FY21 Lake Crockett/Keystone | 21 | NAV | O&M | 2021-09-15 | 30 | 35000 |  | Bucket | Small Business
NWS | FY21 Snohomish River Maint Dredging | 22 | NAV | O&M | 2021-10-16 | 45 | 150000 |  | Pipeline | Small Business
NWS | FY21 Duwamish Waterway Maint Dredging | 22 | NAV | O&M | 2021-12-01 | 40 | 180000 |  | Bucket | Small Business
NWS | FY22 Grays Harbor Inner Harbor Dredging | 22 | NAV | O&M | 2022-07-15 | 180 | 800000 |  | Bucket | Small Business
NWS | FY22 Port Townsend / Keystone Maint Dredging | 22 | NAV | O&M | 2022-07-15 | 25 | 50000 |  | Bucket | Small Business
NWS | FY22 Snohomish River Maint Dredging | 23 | NAV | O&M | 2022-10-16 | 45 | 150000 |  | Bucket | Small Business
NWS | FY23 Grays Harbor Inner Harbor Maint Dredging | 23 | NAV | O&M | 2023-07-15 | 180 | 800000 |  | Bucket | Small Business
NWS | FY23 Swinomish Channel Maint Dredging | 23 | NAV | O&M | 2023-07-15 | 45 | 150000 |  | Bucket | Small Business
NWS | FY23 Quillayute River Maint Dredging | 23 | NAV | O&M | 2023-09-01 | 30 | 75000 |  | Pipeline | Small Business
NWW | Navigation Channel Maintenance Lower Granite Pool & Ice Harbor | 21 | NAV | O&M | 2020-12-15 | 76 | 378500 |  | Bucket | Small Business
SAC | Charleston Post 45 - Entrance - Contract 1 | 18 | NAV | New Work | 2017-12-01 | 851 | 6100000 |  | Hopper | Unrestricted
SAC | AIWW Phase 1 (Charleston-Port Royal) | 18 | NAV | O&M | 2018-04-01 | 240 | 1200000 |  | Pipeline | Small Business
SAC | Charleston Harbor Upper Harbor | 18 | NAV | O&M | 2018-04-01 | 180 | 2000000 |  | Pipeline | Small Business
SAC | Charleston Post 45 - Entrance - Contract 2 | 18 | NAV | New Work | 2018-04-01 | 1200 | 13500000 |  | Pipeline.Bucket | Unrestricted
SAC | Folly Beach | 18 | FRM | O&M | 2018-05-01 | 180 | 750000 |  | Pipeline | Small Business
SAC | Myrtle Beach Reach 1&3 | 18 | FRM | O&M | 2018-07-01 | 180 | 600000 |  | Hopper | Unrestricted
SAC | Myrtle Beach Reach 2 | 18 | FRM | O&M | 2018-07-01 | 180 | 800000 |  | Hopper | Unrestricted
SAC | Folly River | 18 | NAV | O&M | 2018-08-01 | 180 | 200000 |  | Pipeline | Small Business
SAC | AIWW Phase 2 (Georgetown-Port Royal) | 18 | NAV | O&M | 2018-09-01 | 240 | 1700000 |  | Pipeline | Small Business
SAC | Joint Base Charleston (Reimbursable) | 19 | NAV | O&M | 2018-11-01 | 180 | 1500000 |  | Pipeline | Small Business
SAC | Charleston Harbor Lower Harbor | 19 | NAV | O&M | 2019-01-01 | 175 | 1700000 |  | Bucket | Unrestricted
SAC | Charleston Post 45 - Lower Harbor Contract | 20 | NAV | New Work | 2019-03-01 | 365 | 16500000 |  | Pipeline.Bucket | Unrestricted
SAC | Town Creek | 19 | NAV | O&M | 2019-04-01 | 60 | 150000 |  | Pipeline | Government
SAC | Charleston Harbor Upper Harbor | 19 | NAV | O&M | 2019-06-01 | 180 | 2000000 |  | Pipeline | Small Business
SAC | Folly Entrance Channel | 19 | NAV | O&M | 2019-07-01 | 90 | 250000 |  | Pipeline | Government
SAC | Charleston Harbor Lower Harbor | 20 | NAV | O&M | 2020-03-01 | 175 | 1700000 |  | Bucket | Unrestricted
SAC | Charleston Post 45 - Upper Harbor Contract | 20 | NAV | New Work | 2020-03-01 | 270 | 4700000 |  | Pipeline | Unrestricted
SAC | Joint Base Charleston (Reimbursable) | 20 | NAV | O&M | 2020-05-01 | 180 | 1500000 |  | Pipeline | Small Business
SAC | Charleston Habor Entrance | 21 | NAV | O&M | 2020-12-15 | 75 | 1750000 |  | Hopper | Unrestricted
SAC | Charleston Harbor Upper Harbor | 21 | NAV | O&M | 2021-02-21 | 180 | 2000000 |  | Pipeline | Small Business
SAC | Charleston Harbor Lower Harbor | 21 | NAV | O&M | 2021-06-01 | 175 | 1700000 |  | Bucket | Unrestricted
SAC | Joint Base Charleston (Reimbursable) | 22 | NAV | O&M | 2021-12-01 | 180 | 1500000 |  | Pipeline | Small Business
SAC | Charleston Harbor Lower Harbor | 22 | NAV | O&M | 2022-09-01 | 175 | 1700000 |  | Bucket | Unrestricted
SAC | Charleston Harbor Upper Harbor | 22 | NAV | O&M | 2022-09-01 | 180 | 2000000 |  | Pipeline | Small Business
SAC | Murrells Inlet | 22 | NAV | O&M | 2022-09-01 | 120 | 250000 |  | Pipeline | Small Business
SAJ | St Lucie Inlet | 18 | NAV | O&M | 2017-08-30 | 275 | 384000 |  | Bucket | Small Business
SAJ | Tampa Harbor & St Pete Harbor | 18 | NAV | O&M | 2017-11-02 | 146 | 257000 |  | Bucket | Small Business
SAJ | Palm Beach Harbor | 18 | NAV | O&M | 2017-12-08 | 33 | 230000 |  | Pipeline | Unrestricted
SAJ | Tampa Harbor & Manatee Harbor | 18 | NAV | O&M | 2018-01-06 | 84 | 204000 |  | Pipeline | Small Business
SAJ | St Johns County | 18 | FRM | O&M | 2018-01-13 | 103 | 780000 |  | Pipeline | Small Business
SAJ | Kings Bay Entrance Channel | 18 | NAV | O&M | 2018-01-24 | 67 | 1760000 |  | Hopper | Unrestricted
SAJ | USMC Blount Island Command Emergency O&M | 18 | NAV | O&M | 2018-02-02 | 7 | 19843 |  | Bucket | Unrestricted
SAJ | Brevard County | 18 | FRM | O&M | 2018-02-02 | 67 | 1100000 |  | Hopper | Unrestricted
SAJ | Jax Harbor Deepening - Contract A | 18 | NAV | New Work | 2018-02-03 | 534 | 2718000 |  | Bucket | Unrestricted
SAJ | Martin County | 18 | FRM | O&M | 2018-04-02 | 27 | 220000 |  | Hopper | Unrestricted
SAJ | Pinellas County - Sand Key, Treasure Island & Long Key | 18 | FRM | O&M | 2018-04-15 | 176 | 1450500 |  | Pipeline | Unrestricted
SAJ | Ft. Pierce | 18 | FRM | O&M | 2018-04-16 | 44 | 560000 |  | Hopper | Unrestricted
SAJ | Kings Bay Inner Channel | 18 | NAV | O&M | 2018-05-01 | 213 | 1418000 |  | Pipeline | Small Business
SAJ | Palm Beach Harbor - Emergency O&M | 18 | NAV | O&M | 2018-05-23 | 7 | 50000 |  | Combo | Unrestricted
SAJ | Jax Harbor | 18 | NAV | O&M | 2018-06-15 | 76 | 566000 |  | Combo | Unrestricted
SAJ | Horseshoe Cove | 18 | NAV | O&M | 2018-09-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Duval County | 18 | FRM | O&M | 2018-09-01 | 121 | 800000 |  | Pipeline.Hopper | Unrestricted
SAJ | Canaveral Harbor | 18 | NAV | O&M | 2018-10-01 | 120 | 500000 |  | Pipeline | Unrestricted
SAJ | Canaveral Sand Bypass | 18 | NAV | O&M | 2018-10-01 | 180 | 1000000 |  | Pipeline | Unrestricted
SAJ | IWW & Ponce de Leon Inlet | 18 | NAV | O&M | 2018-10-01 | 180 | 436000 |  | Pipeline | Small Business
SAJ | IWW J-M Crossroads & Jupiter | 18 | NAV | O&M | 2018-10-01 | 120 | 500000 |  | Pipeline | Small Business
SAJ | IWW J-M St Augustine & Matanzas | 18 | NAV | O&M | 2018-10-01 | 120 | 500000 |  | Pipeline | Small Business
SAJ | Naples to Big Marco Pass | 18 | NAV | O&M | 2018-10-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Brevard South Reach | 18 | FRM | O&M | 2018-10-01 | 180 | 1000000 |  | Pipeline.Hopper | Unrestricted
SAJ | Broward County - Segment II | 18 | FRM | O&M | 2018-10-01 | 180 | 1000000 |  | Pipeline.Hopper | Unrestricted
SAJ | Broward County - Segment III Phase 2 - AE | 18 | FRM | O&M | 2018-10-01 | 180 | 1000000 |  | Pipeline.Hopper | Unrestricted
SAJ | Tampa Big Bend | 18 | NAV | New Work | 2018-10-15 | 441 | 4022000 |  | Combo | Unrestricted
SAJ | IWW Sawpit Creek | 18 | NAV | O&M | 2018-10-15 | 182 | 500000 |  | Pipeline | Small Business
SAJ | Tampa Harbor - Egmont Cuts 1 & 2 and Mullet Key Channel | 18 | NAV | O&M | 2018-11-01 | 75 | 500000 |  | Combo | Unrestricted
SAJ | Palm Beach Harbor | 18 | NAV | O&M | 2018-11-01 | 59 | 500000 |  | Pipeline.Hopper | Unrestricted
SAJ | Mayport | 19 | NAV | O&M | 2018-11-15 | 120 | 1000000 |  | Combo | Unrestricted
SAJ | Anclote River | 18 | NAV | O&M | 2018-12-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Fort Myers Beach | 18 | NAV | O&M | 2018-12-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Suwannee River | 18 | NAV | O&M | 2018-12-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Brevard Mid Reach | 18 | FRM | O&M | 2018-12-01 | 365 | 4500000 |  | Pipeline.Hopper | Unrestricted
SAJ | Manatee County | 18 | FRM | O&M | 2018-12-01 | 120 | 500000 |  | Pipeline.Hopper | Unrestricted
SAJ | Palm Beach County - Jupiter; Ocean Ridge; Delray; North Boca | 18 | FRM | O&M | 2018-12-01 | 330 | 4000000 |  | Pipeline.Hopper | Unrestricted
SAJ | Jax Harbor Deepening - Contract B | 18 | NAV | New Work | 2019-02-01 | 925 | 5535000 |  | Pipeline.Bucket | Unrestricted
SAJ | Manatee Harbor | 19 | NAV | O&M | 2019-02-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SAJ | Palm Beach Harbor | 19 | NAV | O&M | 2019-02-01 | 60 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Flagler County | 19 | FRM | New Work | 2019-03-01 | 120 | 500000 |  | Pipeline.Hopper | Unrestricted
SAJ | Sarasota County - Lido | 19 | FRM | O&M | 2019-03-01 | 270 | 750000 |  | Pipeline.Hopper | Unrestricted
SAJ | St Johns County | 19 | FRM | O&M | 2019-03-01 | 180 | 1000000 |  | Pipeline.Hopper | Unrestricted
SAJ | St Lucie County | 19 | FRM | O&M | 2019-03-01 | 270 | 750000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Inner Channel | 19 | NAV | O&M | 2019-04-01 | 180 | 1300000 |  | Pipeline | Small Business
SAJ | USMC Blount Island Command | 19 | NAV | O&M | 2019-04-01 | 90 | 100000 |  | Pipeline | Small Business
SAJ | Arecibo Harbor | 19 | NAV | O&M | 2019-06-01 | 180 | 1000000 |  | Combo | Unrestricted
SAJ | Mayaquez Harbor | 19 | NAV | O&M | 2019-06-01 | 180 | 1000000 |  | Combo | Unrestricted
SAJ | Rio Puerto Nuevo | 19 | FRM | New Work | 2019-06-01 | 390 | 200000 |  | Pipeline.Bucket | Unrestricted
SAJ | Dade County | 19 | FRM | O&M | 2019-06-01 | 365 | 4500000 |  | Pipeline.Hopper | Unrestricted
SAJ | Lee County - Gasparilla | 19 | FRM | O&M | 2019-06-01 | 180 | 200000 |  | Pipeline.Hopper | Unrestricted
SAJ | Jax Harbor | 19 | NAV | O&M | 2019-09-01 | 150 | 500000 |  | Combo | Unrestricted
SAJ | Manatee | 19 | NAV | O&M | 2019-09-01 | 30 | 400000 |  | Pipeline | Small Business
SAJ | Tampa Harbor | 20 | NAV | O&M | 2019-10-01 | 180 | 600000 |  | Combo | Unrestricted
SAJ | Miami O&M | 20 | NAV | O&M | 2019-11-01 | 60 | 300000 |  | Combo | Unrestricted
SAJ | Naval Station Mayport | 20 | NAV | O&M | 2019-11-01 | 150 | 1000000 |  | Combo | Unrestricted
SAJ | Port Everglades O&M | 20 | NAV | O&M | 2019-11-01 | 45 | 300000 |  | Combo | Unrestricted
SAJ | Ft. Pierce | 20 | FRM | O&M | 2019-11-01 | 120 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Entrance Channel | 20 | NAV | O&M | 2019-12-01 | 90 | 1300000 |  | Hopper | Unrestricted
SAJ | Flagler County | 20 | FRM | O&M | 2019-12-01 | 120 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Palm Beach County - Jupiter/Carlin | 20 | FRM | O&M | 2019-12-01 | 120 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Jax Harbor Deepening - Contract C | 20 | NAV | New Work | 2020-01-01 | 180 | 1400000 |  | Pipeline.Bucket | Unrestricted
SAJ | Port Everglades Deepening | 20 | NAV | New Work | 2020-01-01 | 270 | 5000000 |  | Pipeline.Bucket | Unrestricted
SAJ | Palm Beach Harbor | 20 | NAV | O&M | 2020-02-01 | 60 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Inner Channel | 20 | NAV | O&M | 2020-04-01 | 180 | 1300000 |  | Pipeline | Small Business
SAJ | USMC Blount Island Command | 20 | NAV | O&M | 2020-04-01 | 90 | 100000 |  | Pipeline | Small Business
SAJ | Jax Harbor | 20 | NAV | O&M | 2020-09-01 | 150 | 450000 |  | Combo | Unrestricted
SAJ | Tampa Harbor | 21 | NAV | O&M | 2020-10-01 | 180 | 600000 |  | Combo | Unrestricted
SAJ | San Juan | 21 | NAV | O&M | 2020-10-01 | 180 | 600000 |  | Pipeline.Bucket | Unrestricted
SAJ | Kings Bay Entrance Channel | 21 | NAV | O&M | 2020-12-01 | 90 | 1300000 |  | Hopper | Unrestricted
SAJ | Jax Harbor Deepening - Contract D | 21 | NAV | New Work | 2021-01-01 | 180 | 1400000 |  | Pipeline.Bucket | Unrestricted
SAJ | Palm Beach Harbor | 21 | NAV | O&M | 2021-02-01 | 60 | 450000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Inner Channel | 21 | NAV | O&M | 2021-04-01 | 180 | 1300000 |  | Pipeline | Small Business
SAJ | USMC Blount Island Command | 21 | NAV | O&M | 2021-04-01 | 90 | 100000 |  | Pipeline | Small Business
SAJ | Canaveral Harbor | 21 | NAV | O&M | 2021-07-01 | 180 | 450000 |  | Bucket | Unrestricted
SAJ | Jax Harbor | 21 | NAV | O&M | 2021-09-01 | 150 | 450000 |  | Combo | Unrestricted
SAJ | Tampa Harbor | 22 | NAV | O&M | 2021-10-01 | 180 | 600000 |  | Combo | Unrestricted
SAJ | Naval Station Mayport | 22 | NAV | O&M | 2021-11-01 | 150 | 1000000 |  | Combo | Unrestricted
SAJ | Ft. Pierce | 22 | FRM | O&M | 2021-11-01 | 120 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Entrance Channel | 22 | NAV | O&M | 2021-12-01 | 90 | 1300000 |  | Hopper | Unrestricted
SAJ | Palm Beach County - Delray | 22 | FRM | O&M | 2021-12-01 | 120 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | St. John's County | 22 | FRM | O&M | 2021-12-01 | 135 | 800000 |  | Pipeline.Hopper | Unrestricted
SAJ | Palm Beach Harbor | 22 | NAV | O&M | 2022-02-01 | 60 | 350000 |  | Pipeline.Hopper | Unrestricted
SAJ | Kings Bay Inner Channel | 22 | NAV | O&M | 2022-04-01 | 180 | 1300000 |  | Pipeline | Small Business
SAJ | USMC Blount Island Command | 22 | NAV | O&M | 2022-04-01 | 90 | 100000 |  | Pipeline | Small Business
SAJ | Jax Harbor | 22 | NAV | O&M | 2022-09-01 | 150 | 450000 |  | Combo | Unrestricted
SAJ | Manatee | 22 | NAV | O&M | 2022-09-01 | 30 | 400000 |  | Pipeline | Small Business
SAJ | Kings Bay Entrance Channel | 23 | NAV | O&M | 2022-12-01 | 90 | 1300000 |  | Hopper | Unrestricted
SAJ | Pinellas County - Treasure Island & Long Key | 23 | FRM | O&M | 2022-12-01 | 120 | 550000 |  | Pipeline.Hopper | Unrestricted
SAM | MSCIP - Camille Cut | 18 | FRM | New Work | 2017-09-01 | 270 | 7000000 |  | Hopper | Unrestricted
SAM | Mobile Bay/River/Theodore | 18 | NAV | O&M | 2018-02-01 | 100 | 4500000 |  | Pipeline | Unrestricted
SAM | Pascagoula Entrance | 18 | NAV | O&M | 2018-03-01 | 30 | 250000 |  | Hopper | Unrestricted
SAM | GIWW | 18 | NAV | O&M | 2018-04-01 | 90 | 1500000 |  | Pipeline | Unrestricted
SAM | Pascagoula Harbor | 18 | NAV | O&M | 2018-05-01 | 30 | 400000 |  | Pipeline | Unrestricted
SAM | BW&T | 18 | NAV | O&M | 2018-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Dauphin Island, Pass Drury and Fort Gaines | 18 | NAV | O&M | 2018-07-01 | 30 | 20000 |  | Pipeline | Small Business
SAM | Tenn-Tom | 18 | NAV | O&M | 2018-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Mobile Harbor Rental #1 | 18 | NAV | O&M | 2018-07-15 | 210 | 1500000 |  | Hopper | Unrestricted
SAM | Mobile Bar | 18 | NAV | O&M | 2018-09-01 | 60 | 1200000 |  | Hopper | Unrestricted
SAM | MSCIP - Camille Cut Phase 2 | 19 | FRM | New Work | 2018-09-01 | 270 | 5500000 |  | Hopper | Unrestricted
SAM | Dauphin Island, Village Channel | 18 | NAV | O&M | 2018-09-01 | 30 | 50000 |  | Pipeline | Small Business
SAM | Biloxi, East Access | 19 | NAV | O&M | 2018-10-01 | 60 | 800000 |  | Pipeline | Unrestricted
SAM | Dog and Fowl Rivers | 19 | NAV | O&M | 2018-10-01 | 45 | 100000 |  | Pipeline | Small Business
SAM | East Pass, FL | 19 | NAV | O&M | 2018-10-15 | 30 | 100000 |  | Pipeline | Unrestricted
SAM | Bayou LaBatre | 19 | NAV | O&M | 2018-11-01 | 30 | 500000 |  | Pipeline | Unrestricted
SAM | Wolf, Jordan and Bayou Portage Rivers | 19 | NAV | O&M | 2018-11-15 | 45 | 100000 |  | Pipeline | Small Business
SAM | Bon Secour | 19 | NAV | O&M | 2018-12-01 | 30 | 100000 |  | Pipeline | Unrestricted
SAM | Perdido Pass | 19 | NAV | O&M | 2019-01-01 | 30 | 500000 |  | Pipeline | Unrestricted
SAM | Mobile Bay/River/Theodore | 19 | NAV | O&M | 2019-02-01 | 200 | 4500000 |  | Pipeline | Unrestricted
SAM | Mobile Harbor Rental #1 | 19 | NAV | O&M | 2019-02-15 | 210 | 1500000 |  | Hopper | Unrestricted
SAM | Biloxi, Back Bay | 19 | NAV | O&M | 2019-02-15 | 60 | 100000 |  | Pipeline | Small Business
SAM | Panama City Deepening | 19 | NAV | New Work | 2019-04-01 | 180 | 400000 |  | Pipeline | Unrestricted
SAM | Tenn-Tom | 19 | NAV | O&M | 2019-04-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Pascagoula Harbor | 19 | NAV | O&M | 2019-06-01 | 90 | 2000000 |  | Pipeline | Unrestricted
SAM | BW&T | 19 | NAV | O&M | 2019-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | MSCIP - Camille Cut Phase 3 | 20 | FRM | New Work | 2019-09-01 | 270 | 5500000 |  | Hopper | Unrestricted
SAM | GIWW | 20 | NAV | O&M | 2019-11-01 | 90 | 1500000 |  | Pipeline | Unrestricted
SAM | Escambia | 20 | NAV | O&M | 2020-02-01 | 60 | 400000 |  | Pipeline | Unrestricted
SAM | Mobile Harbor Rental #1 | 20 | NAV | O&M | 2020-02-15 | 210 | 1500000 |  | Hopper | Unrestricted
SAM | Port St. Joe | 20 | NAV | O&M | 2020-02-15 | 60 | 600000 |  | Pipeline | Unrestricted
SAM | Bayou Cassote Widening | 20 | NAV | New Work | 2020-04-01 | 270 | 3400000 |  | Pipeline | Unrestricted
SAM | Tenn-Tom | 20 | NAV | O&M | 2020-04-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Port St. Joe | 20 | NAV | O&M | 2020-05-15 | 180 | 1650000 |  | Hopper | Unrestricted
SAM | Pascagoula Harbor | 20 | NAV | O&M | 2020-06-01 | 120 | 3000000 |  | Pipeline | Unrestricted
SAM | BW&T | 20 | NAV | O&M | 2020-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | MSCIP - Camille Cut Phase 4 | 20 | FRM | New Work | 2020-09-01 | 120 | 1100000 |  | Pipeline | Unrestricted
SAM | GIWW | 21 | NAV | O&M | 2020-11-01 | 90 | 1500000 |  | Pipeline | Unrestricted
SAM | Biloxi | 21 | NAV | O&M | 2021-02-01 | 60 | 1000000 |  | Pipeline | Unrestricted
SAM | Mobile Bay/River/Theodore | 21 | NAV | O&M | 2021-02-01 | 200 | 4500000 |  | Pipeline | Unrestricted
SAM | Mobile Harbor Rental #1 | 21 | NAV | O&M | 2021-02-15 | 210 | 1500000 |  | Hopper | Unrestricted
SAM | Tenn-Tom | 21 | NAV | O&M | 2021-04-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Mobile Bar | 21 | NAV | O&M | 2021-05-01 | 35 | 700000 |  | Hopper | Unrestricted
SAM | Mobile Harbor Deepening | 21 | NAV | New Work | 2021-05-01 | 365 | 10000000 |  | Pipeline | Unrestricted
SAM | Pascagoula Entrance | 21 | NAV | O&M | 2021-06-01 | 60 | 1000000 |  | Hopper | Unrestricted
SAM | Pascagoula Harbor | 21 | NAV | O&M | 2021-06-01 | 120 | 3000000 |  | Pipeline | Unrestricted
SAM | BW&T | 21 | NAV | O&M | 2021-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | GIWW | 21 | NAV | O&M | 2021-11-01 | 90 | 1500000 |  | Pipeline | Unrestricted
SAM | Mobile Bay/River/Theodore | 22 | NAV | O&M | 2022-02-01 | 200 | 4500000 |  | Pipeline | Unrestricted
SAM | Mobile Harbor Rental #1 | 22 | NAV | O&M | 2022-02-15 | 210 | 1500000 |  | Hopper | Unrestricted
SAM | Tenn-Tom | 22 | NAV | O&M | 2022-04-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | Pascagoula Harbor | 22 | NAV | O&M | 2022-06-01 | 90 | 2000000 |  | Pipeline | Unrestricted
SAM | BW&T | 22 | NAV | O&M | 2022-07-01 | 90 | 750000 |  | Pipeline | Unrestricted
SAM | GIWW | 23 | NAV | O&M | 2022-11-01 | 90 | 1500000 |  | Pipeline | Unrestricted
SAM | Gulfport Entrance | 18 | NAV | O&M | 2017-10-01 | 210 | 4000000 |  | Hopper | Unrestricted
SAM | Gulfport Inner | 18 | NAV | O&M | 2018-06-15 | 105 | 2500000 |  | Pipeline | Unrestricted
SAM | Pananma City | 19 | NAV | O&M | 2018-11-15 | 30 | 400000 |  | Pipeline | Unrestricted
SAM | Pensacola Inner | 19 | NAV | O&M | 2018-11-15 | 30 | 400000 |  | Pipeline | Unrestricted
SAM | Pananma City | 21 | NAV | O&M | 2020-11-15 | 30 | 400000 |  | Pipeline | Unrestricted
SAM | Gulfport Entrance | 21 | NAV | O&M | 2021-04-01 | 60 | 2000000 |  | Hopper | Unrestricted
SAM | Gulfport Inner | 22 | NAV | O&M | 2021-10-15 | 210 | 3500000 |  | Pipeline | Unrestricted
SAM | Pensacola Inner | 22 | NAV | O&M | 2021-11-15 | 30 | 400000 |  | Pipeline | Unrestricted
SAM | Pensacola Entrance | 22 | NAV | O&M | 2021-12-15 | 60 | 1000000 |  | Hopper | Unrestricted
SAS | Atlantic Intracoastal Waterway, GA | 18 | NAV | O&M | 2018-09-01 | 180 | 400000 |  | Pipeline | Small Business
SAS | SHEP Inner Harbor - Contract 1 | 19 | NAV | New Work | 2018-12-01 | 365 | 4400000 |  | Pipeline | Unrestricted
SAS | Tybee Island | 20 | FRM | O&M | 2019-11-01 | 165 | 1000000 |  | Pipeline.Hopper | Unrestricted
SAS | SHEP Inner Harbor - Contract 2 | 20 | NAV | New Work | 2019-12-01 | 760 | 8300000 |  | Pipeline | Unrestricted
SAS | Savannah Inner Harbor | 18 | NAV | O&M | 2018-08-01 | 365 | 5500000 |  | Pipeline | Unrestricted
SAS | Brunswick Inner Harbor | 18 | NAV | O&M | 2018-09-01 | 45 | 400000 |  | Pipeline | Small Business
SAS | Savannah Inner Harbor | 19 | NAV | O&M | 2019-08-01 | 365 | 5500000 |  | Pipeline | Unrestricted
SAS | Brunswick Inner Harbor | 19 | NAV | O&M | 2019-09-01 | 45 | 400000 |  | Pipeline | Small Business
SAS | Savannah Harbor Entrance | 20 | NAV | O&M | 2019-12-01 | 45 | 1000000 |  | Hopper | Unrestricted
SAS | Brunswick Harbor Entrance | 20 | NAV | O&M | 2020-01-02 | 90 | 1500000 |  | Hopper | Unrestricted
SAS | Savannah Inner Harbor | 20 | NAV | O&M | 2020-08-01 | 365 | 5500000 |  | Pipeline | Unrestricted
SAS | Brunswick Inner Harbor | 20 | NAV | O&M | 2020-09-01 | 45 | 400000 |  | Pipeline | Small Business
SAS | Savannah Harbor Entrance | 21 | NAV | O&M | 2020-12-01 | 45 | 1000000 |  | Hopper | Unrestricted
SAS | Brunswick Harbor Entrance | 21 | NAV | O&M | 2021-01-02 | 90 | 1500000 |  | Hopper | Unrestricted
SAS | Savannah Inner Harbor | 21 | NAV | O&M | 2021-08-01 | 365 | 5500000 |  | Pipeline | Unrestricted
SAS | Brunswick Inner Harbor | 21 | NAV | O&M | 2021-09-01 | 45 | 400000 |  | Pipeline | Small Business
SAS | Savannah Harbor Entrance | 22 | NAV | O&M | 2021-12-01 | 45 | 1000000 |  | Hopper | Unrestricted
SAS | Brunswick Harbor Entrance | 22 | NAV | O&M | 2022-01-02 | 90 | 1500000 |  | Hopper | Unrestricted
SAS | Savannah Inner Harbor | 22 | NAV | O&M | 2022-08-01 | 365 | 5500000 |  | Pipeline | Unrestricted
SAS | Brunswick Inner Harbor | 22 | NAV | O&M | 2022-09-01 | 45 | 400000 |  | Pipeline | Small Business
SAW | Wilmington Harbor Inner Ocean Bar | 18 | NAV | O&M | 2018-05-01 | 90 | 1200000 |  | Pipeline | Unrestricted
SAW | Morehead City Cutoff & Range B | 18 | NAV | O&M | 2018-06-01 | 90 | 1000000 |  | Pipeline | Unrestricted
SAW | Wilmington Harbor Anchorage Basin | 18 | NAV | O&M | 2018-09-01 | 120 | 1425000 |  | Pipeline | Small Business
SAW | Carolina Beach & Vicinity (Carolina Beach Portion) | 19 | FRM | O&M | 2018-11-16 | 60 | 900000 |  | Pipeline | Unrestricted
SAW | SAD Regional Hopper - Wilmington Harbor, Morehead City, Savannah Bruswick Harbor Entrances | 19 | NAV | O&M | 2018-12-01 | 135 | 900000 |  | Hopper | Unrestricted
SAW | Atlantic Intracoastal Waterway. NC (AIWW, NC) | 19 | NAV | O&M | 2018-12-01 | 75 | 500000 |  | Pipeline | Small Business
SAW | Carolina Beach & Vicinity (Area South (Kure Beach) Portion) | 19 | FRM | O&M | 2018-12-01 | 60 | 600000 |  | Pipeline | Unrestricted
SAW | Morehead City Inner Harbor | 19 | NAV | O&M | 2019-01-01 | 135 | 325000 |  | Pipeline | Small Business
SAW | Wilmington Harbor Mid River | 19 | NAV | O&M | 2019-02-01 | 150 | 1000000 |  | Hopper.Bucket | Unrestricted
SAW | Wilmington Harbor Anchorage Basin | 19 | NAV | O&M | 2019-09-01 | 120 | 1425000 |  | Pipeline | Small Business
SAW | Wilmington Harbor Inner Ocean Bar | 20 | NAV | O&M | 2019-11-16 | 90 | 1000000 |  | Pipeline | Unrestricted
SAW | Wilmington Harbor Entrance | 20 | NAV | O&M | 2019-12-01 | 60 | 750000 |  | Hopper | Unrestricted
SAW | Morehead City Ocean Bar | 20 | NAV | O&M | 2020-01-01 | 75 | 1500000 |  | Combo | Unrestricted
SAW | Wilmington Harbor Anchorage Basin | 20 | NAV | O&M | 2020-09-01 | 120 | 1425000 |  | Pipeline | Small Business
SAW | Brunswick County Beaches (Ocean Isle Beach Portion) | 21 | FRM | O&M | 2020-11-16 | 60 | 350000 |  | Pipeline | Unrestricted
SAW | Wilmington Harbor Entrance | 21 | NAV | O&M | 2020-12-01 | 60 | 750000 |  | Hopper | Unrestricted
SAW | Atlantic Intracoastal Waterway. NC (AIWW, NC) | 21 | NAV | O&M | 2020-12-01 | 75 | 500000 |  | Pipeline | Small Business
SAW | Morehead City Ocean Bar | 21 | NAV | O&M | 2021-01-01 | 75 | 1500000 |  | Combo | Unrestricted
SAW | Wilmington Harbor Mid River | 21 | NAV | O&M | 2021-02-01 | 150 | 1000000 |  | Hopper.Bucket | Unrestricted
SAW | Wilmington Harbor Anchorage Basin | 21 | NAV | O&M | 2021-09-01 | 120 | 1425000 |  | Pipeline | Small Business
SAW | Carolina Beach & Vicinity (Carolina Beach Portion) | 22 | FRM | O&M | 2021-11-16 | 60 | 900000 |  | Pipeline | Unrestricted
SAW | Manteo Interior Channels | 22 | NAV | O&M | 2021-11-16 | 120 | 600000 |  | Pipeline | Small Business
SAW | Rollinson Channel | 22 | NAV | O&M | 2021-11-16 | 120 | 110000 |  | Pipeline | Small Business
SAW | Silver Lake Harbor | 22 | NAV | O&M | 2021-11-16 | 120 | 110000 |  | Pipeline | Small Business
SAW | Wilmington Harbor Inner Ocean Bar | 22 | NAV | O&M | 2021-11-16 | 90 | 1000000 |  | Pipeline | Unrestricted
SAW | Wrightsville Beach | 22 | FRM | O&M | 2021-11-16 | 45 | 600000 |  | Pipeline | Unrestricted
SAW | Wilmington Harbor Entrance | 22 | NAV | O&M | 2021-12-01 | 60 | 750000 |  | Hopper | Unrestricted
SAW | Carolina Beach & Vicinity (Area South (Kure Beach) Portion) | 22 | FRM | O&M | 2021-12-01 | 60 | 600000 |  | Pipeline | Unrestricted
SAW | Morehead City Ocean Bar | 22 | NAV | O&M | 2022-01-01 | 75 | 1500000 |  | Combo | Unrestricted
SAW | Wilmington Harbor Anchorage Basin | 22 | NAV | O&M | 2022-09-01 | 120 | 1425000 |  | Pipeline | Small Business
SAW | Atlantic Intracoastal Waterway. NC (AIWW, NC) | 23 | NAV | O&M | 2022-12-01 | 75 | 450000 |  | Pipeline | Small Business
SAW | Morehead City Ocean Bar | 23 | NAV | O&M | 2023-01-01 | 75 | 1500000 |  | Combo | Unrestricted
SAW | Wilmington Harbor Mid River | 23 | NAV | O&M | 2023-02-01 | 150 | 1000000 |  | Hopper.Bucket | Unrestricted
SPL | Channel Islands Harbor - Year 1 of 3 year contract | 19 | NAV | O&M | 2018-10-01 | 120 | 1800000 |  | Pipeline | Unrestricted
SPL | Santa Barbara Harbor - Year 3 of 3 year contract | 19 | NAV | O&M | 2018-12-01 | 90 | 240000 |  | Pipeline | Unrestricted
SPL | Port Hueneme | 19 | NAV | O&M | 2019-01-01 | 30 | 150000 |  | Pipeline | Unrestricted
SPL | Ventura Harbor - Year 1 of 3 year contract | 19 | NAV | O&M | 2019-02-01 | 90 | 600000 |  | Pipeline | Unrestricted
SPL | Port of Los Angeles-Long Beach (LA-LB) | 19 | NAV | O&M | 2019-03-01 | 90 | 350000 |  | Bucket | Small Business
SPL | Oceanside Harbor - Year 3 of 3 year contract | 19 | NAV | O&M | 2019-04-01 | 60 | 300000 |  | Pipeline | Unrestricted
SPL | San Diego Harbor | 19 | NAV | O&M | 2019-08-01 | 90 | 300000 |  | Bucket | Unrestricted
SPL | Newport Harbor | 20 | NAV | O&M | 2019-12-01 | 45 | 150000 |  | Bucket | Small Business
SPL | Santa Barbara Harbor - Year 1 of 3 year contract | 20 | NAV | O&M | 2019-12-01 | 90 | 240000 |  | Pipeline | Unrestricted
SPL | Ventura Harbor - Year 2 of 3 year contract | 20 | NAV | O&M | 2020-02-01 | 90 | 600000 |  | Pipeline | Unrestricted
SPL | Oceanside Harbor - Year 1 of 3 year contract | 20 | NAV | O&M | 2020-04-01 | 60 | 300000 |  | Pipeline | Unrestricted
SPL | San Diego Harbor | 20 | NAV | O&M | 2020-08-01 | 90 | 300000 |  | Bucket | Unrestricted
SPL | Channel Islands Harbor - Year 2 of 3 year contract | 21 | NAV | O&M | 2020-10-01 | 120 | 1800000 |  | Pipeline | Unrestricted
SPL | Santa Barbara Harbor - Year 2 of 3 year contract | 21 | NAV | O&M | 2020-12-01 | 90 | 240000 |  | Pipeline | Unrestricted
SPL | Ventura Harbor - Year 3 of 3 year contract | 21 | NAV | O&M | 2021-02-01 | 90 | 600000 |  | Pipeline | Unrestricted
SPL | Oceanside Harbor - Year 2 of 3 year contract | 21 | NAV | O&M | 2021-04-01 | 60 | 300000 |  | Pipeline | Unrestricted
SPL | Santa Barbara Harbor - Year 3 of 3 year contract | 22 | NAV | O&M | 2021-12-01 | 90 | 240000 |  | Pipeline | Unrestricted
SPL | Ventura Harbor - Year 1 of 3 year contract | 22 | NAV | O&M | 2022-02-01 | 90 | 600000 |  | Pipeline | Unrestricted
SPL | Marina Del Rey | 22 | NAV | O&M | 2022-02-01 | 120 | 500000 |  | Pipeline.Bucket | Small Business
SPL | Oceanside Harbor - Year 3 of 3 year contract | 22 | NAV | O&M | 2022-04-01 | 60 | 300000 |  | Pipeline | Unrestricted
SPL | Channel Islands Harbor - Year 3 of 3 year contract | 23 | NAV | O&M | 2022-10-01 | 120 | 1800000 |  | Pipeline | Unrestricted
SPL | Morro Bay Harbor | 23 | NAV | O&M | 2022-11-01 | 120 | 200000 |  | Pipeline | Small Business
SPL | Santa Barbara Harbor - Year 1 of 3 year contract | 23 | NAV | O&M | 2022-12-01 | 90 | 240000 |  | Pipeline | Unrestricted
SPL | Ventura Harbor - Year 2 of 3 year contract | 23 | NAV | O&M | 2023-02-01 | 90 | 600000 |  | Pipeline | Unrestricted
SPL | Port of Los Angeles-Long Beach (LA-LB) | 23 | NAV | O&M | 2023-03-01 | 90 | 350000 |  | Bucket | Small Business
SPL | Oceanside Harbor - Year 1 of 3 year contract | 23 | NAV | O&M | 2023-04-01 | 60 | 300000 |  | Pipeline | Unrestricted
SPN | Sacramento River | 18 | NAV | O&M | 2018-08-01 | 105 | 350000 |  | Pipeline | Small Business
SPN | Oakland Harbor | 18 | NAV | O&M | 2018-09-01 | 105 | 750000 |  | Bucket | Unrestricted
SPN | Richmond Harbor Inner | 18 | NAV | O&M | 2018-09-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Suisun Channel | 18 | NAV | O&M | 2018-09-01 | 60 | 250000 |  | Bucket | Unrestricted
SPN | Redwood City Harbor | 19 | NAV | O&M | 2019-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Richmond Harbor Inner | 19 | NAV | O&M | 2019-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Oakland Harbor- Year 1 of 3 year Contract | 19 | NAV | O&M | 2019-08-01 | 90 | 750000 |  | Bucket | Unrestricted
SPN | Suisun Channel | 19 | NAV | O&M | 2019-08-01 | 60 | 250000 |  | Bucket | Unrestricted
SPN | Sacramento River / San Joaquin Port of Stockton | 19 | NAV | O&M | 2019-08-01 | 105 | 350000 |  | Pipeline | Small Business
SPN | Richmond Harbor Inner | 20 | NAV | O&M | 2020-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Crescent City Harbor | 20 | NAV | O&M | 2020-07-01 | 30 | 50000 |  | Pipeline | Small Business
SPN | Oakland Harbor- Year 2 of 3 year Contract | 20 | NAV | O&M | 2020-08-01 | 90 | 750000 |  | Bucket | Unrestricted
SPN | Suisun Channel | 20 | NAV | O&M | 2020-08-01 | 60 | 250000 |  | Bucket | Unrestricted
SPN | Sacramento River / San Joaquin Port of Stockton | 20 | NAV | O&M | 2020-08-01 | 105 | 350000 |  | Pipeline | Small Business
SPN | Petaluma River | 20 | NAV | O&M | 2020-08-01 | 60 | 100000 |  | Pipeline.Bucket | Small Business
SPN | Redwood City Harbor | 21 | NAV | O&M | 2021-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Richmond Harbor Inner | 21 | NAV | O&M | 2021-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Jack D. Maltester (San Leandro) | 21 | NAV | O&M | 2021-08-01 | 30 | 20000 |  | Bucket | Small Business
SPN | Moss Landing and Harbor | 21 | NAV | O&M | 2021-08-01 | 30 | 20000 |  | Bucket | Small Business
SPN | Oakland Harbor- Year 3 of 3 year Contract | 21 | NAV | O&M | 2021-08-01 | 90 | 750000 |  | Bucket | Unrestricted
SPN | Suisun Channel | 21 | NAV | O&M | 2021-08-01 | 60 | 250000 |  | Bucket | Unrestricted
SPN | Sacramento River / San Joaquin Port of Stockton | 21 | NAV | O&M | 2021-08-01 | 105 | 350000 |  | Pipeline | Small Business
SPN | Richmond Harbor Inner | 22 | NAV | O&M | 2022-06-01 | 45 | 350000 |  | Bucket | Unrestricted
SPN | Noyo River and Harbor | 22 | NAV | O&M | 2022-08-01 | 30 | 20000 |  | Bucket | Small Business
SPN | Oakland Harbor- Year 1 of 3 year Contract | 22 | NAV | O&M | 2022-08-01 | 90 | 750000 |  | Bucket | Unrestricted
SPN | Suisun Channel | 22 | NAV | O&M | 2022-08-01 | 60 | 250000 |  | Bucket | Unrestricted
SPN | Sacramento River / San Joaquin Port of Stockton | 22 | NAV | O&M | 2022-08-01 | 105 | 350000 |  | Pipeline | Small Business
SPN | San Rafael | 22 | NAV | O&M | 2022-08-01 | 60 | 100000 |  | Pipeline.Bucket | Small Business
SWG | Houston Ship Channel - Exxon to Carpenters Emergency Dredging | 18 | NAV | O&M | 2018-04-19 | 485 | 1388800 |  | Pipeline
SWG | Channel to Victoria - Maint Pipeline Dredging (Lower Reach, Sea Drift) | 18 | NAV | O&M | 2018-06-15 | 220 | 1500000 |  | Pipeline
SWG | Brazos Island Harbor - Main Channel | 19 | NAV | O&M | 2018-06-26 | 210 | 1500000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Across Aransas Bay | 18 | NAV | O&M | 2018-06-28 | 108 | 1749000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Channel Improvement Project (Entrance Channel) | 18 | NAV | New Work | 2018-07-09 | 365 | 6400000 |  | Combo | Unrestricted
SWG | Sabine-Neches Waterway - Outer Bar & Bank | 18 | NAV | O&M | 2018-07-20 | 46 | 2409000 |  | Hopper
SWG | Freeport Harbor - Jetty Channel and Inside Channel | 18 | NAV | O&M | 2018-08-15 | 122 | 2500000 |  | Hopper
SWG | Gulf Intracoastal Waterway - Rollover to Causeway & Bolivar Flare | 18 | NAV | O&M | 2018-09-19 | 150 | 1200000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Freeport to Caney Creek, Brazos River Crossing | 18 | NAV | O&M | 2018-09-27 | 290 | 1200000 |  | Pipeline
SWG | BIH - Jetty Channel with beach placement | 18 | NAV | O&M | 2018-09-28 | 100 | 400000 |  | Pipeline.Hopper
SWG | Gulf Intracoastal Waterway - Corpus Christi to Port Isabel / Channel to Harlingen | 18 | NAV | O&M | 2018-10-03 | 180 | 1600000 |  | Pipeline
SWG | Houston Ship Channel - Bayport to Morgans & Bayport | 18 | NAV | O&M | 2018-10-10 | 270 | 1950000 |  | Pipeline
SWG | Chocolate Bayou - Maintenance Dredging | 19 | NAV | O&M | 2018-10-14 | 240 | 700000 |  | Pipeline
SWG | Matagorda Ship Channel - Matagorda Pen. To Point Comfort | 19 | NAV | O&M | 2018-10-23 | 213 | 2000000 |  | Pipeline
SWG | Galveston Harbor - Galveston Inner Harbor Dredging | 19 | NAV | O&M | 2018-10-25 | 110 | 1000000 |  | Hopper.Bucket
SWG | Houston Ship Channel - Morgans to Exxon | 19 | NAV | O&M | 2018-10-26 | 270 | 1400000 |  | Pipeline
SWG | Sabine-Neches Waterway - SNWW Maintenance Dredging | 19 | NAV | O&M | 2018-10-26 | 157 | 1864000 |  | Pipeline
SWG | Cedar Bayou - Maintenance Dredging | 19 | NAV | O&M | 2018-11-01 | 106 | 300000 |  | Pipeline
SWG | GIWW - Caney Creek to Upper Matagorda Bay; Brazos River Crossing | 19 | NAV | O&M | 2019-03-22 | 180 | 800000 |  | Pipeline
SWG | Houston Ship Channel-Boggy Bayou to Greens and Greens Bayou | 19 | NAV | O&M | 2019-03-29 | 261 | 1000000 |  | Pipeline
SWG | Houston Ship Channel-Sims Bayou to Turning Basin and Light Draft | 19 | NAV | O&M | 2019-03-31 | 457 | 1500000 |  | Pipeline
SWG | GIWW - Across San Antonio Bay / Matagorda Bay to Corpus Christi; GIWW / MSC intersection | 19 | NAV | O&M | 2019-04-02 | 150 | 1200000 |  | Pipeline.Hopper
SWG | Galveston Harbor - Galveston Entrance Channel and HSC Bolivar to Redfish | 19 | NAV | O&M | 2019-04-15 | 183 | 2000000 |  | Hopper
SWG | Houston Ship Channel-Redfish to Beacon 78 with Bayport Flare (HOPPER OFFSHORE) | 19 | NAV | O&M | 2019-05-15 | 214 | 2000000 |  | Hopper
SWG | Freeport Harbor - Jetty Channel and Inside Channel | 19 | NAV | O&M | 2019-06-28 | 136 | 2600000 |  | Hopper
SWG | Texas City Ship Channel - Main Channel & Turning Basin | 19 | NAV | O&M | 2019-08-12 | 360 | 1800000 |  | Pipeline
SWG | Sabine-Neches Waterway - Port Arthur Canal, Junction, Taylors Bayou | 19 | NAV | O&M | 2019-08-17 | 186 | 2000000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Inner Basin to Viola | 19 | NAV | O&M | 2019-08-29 | 230 | 2500000 |  | Pipeline
SWG | GIWW - Corpus Christi to Port Isabel & Channel to Harlingen | 19 | NAV | O&M | 2019-08-29 | 210 | 1500000 |  | Pipeline
SWG | Brazos Island Harbor - Jetty Channel | 19 | NAV | O&M | 2019-09-25 | 110 | 500000 |  | Pipeline
SWG | Houston Ship Channel-Exxon to Boggy Bayou and Jacintoport | 19 | NAV | O&M | 2019-09-29 | 77 | 1500000 |  | Pipeline
SWG | Matagorda Ship Channel - Matagorda Pen. To Point Comfort | 19 | NAV | O&M | 2019-09-30 | 226 | 2000000 |  | Pipeline
SWG | GIWW - High Island to Rollover; Bolivar Flare; Channel to Port Bolivar | 19 | NAV | O&M | 2019-10-01 | 150 | 800000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Causeway to Bastrop | 20 | NAV | O&M | 2020-04-01 | 214 | 800000 |  | Pipeline
SWG | Houston Ship Channel - Morgans to Exxon & Barbours Flare | 20 | NAV | O&M | 2020-04-01 | 214 | 2200000 |  | Pipeline
SWG | Galveston Harbor - Galveston Inner Harbor Dredging | 20 | NAV | O&M | 2020-05-01 | 153 | 1000000 |  | Hopper.Bucket
SWG | Channel to Victoria - Lower Reach | 20 | NAV | O&M | 2020-05-01 | 153 | 600000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Across Aransas Bay | 20 | NAV | O&M | 2020-05-01 | 153 | 1200000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Corpus Christi to Port Isabel / Channel to Harlingen | 20 | NAV | O&M | 2020-05-01 | 214 | 1500000 |  | Pipeline
SWG | Houston Ship Channel - Sims to Turning Basin | 20 | NAV | O&M | 2020-06-01 | 245 | 1400000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Freeport to Caney Creek | 20 | NAV | O&M | 2020-07-01 | 153 | 1000000 |  | Pipeline
SWG | Sabine-Neches Waterway - Port Arthur Canal, Junction, Taylors Bayou | 20 | NAV | O&M | 2020-07-01 | 215 | 1400000 |  | Pipeline
SWG | Freeport Harbor - Jetty Channel and Inside Channel | 20 | NAV | O&M | 2020-08-01 | 92 | 1800000 |  | Hopper
SWG | Sabine-Neches Waterway - Outer Bar & Bank & Pass Channel | 20 | NAV | O&M | 2020-09-01 | 91 | 2000000 |  | Hopper
SWG | Brazos Island Harbor - Jetty Channel | 20 | NAV | O&M | 2020-09-01 | 122 | 500000 |  | Pipeline
SWG | Houston Ship Channel - Bayport Ship Channel & Flare | 20 | NAV | O&M | 2020-09-01 | 242 | 1700000 |  | Pipeline
SWG | Matagorda Ship Channel - Matagorda Pen. To Point Comfort | 20 | NAV | O&M | 2020-09-01 | 153 | 2400000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Inner Basin to Viola | 21 | NAV | O&M | 2020-10-01 | 212 | 2500000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Rollover to Causeway and Bolivar Flare | 21 | NAV | O&M | 2020-10-01 | 182 | 800000 |  | Pipeline
SWG | Galveston Harbor - Galveston Entrance Channel and HSC Bolivar to Redfish | 21 | NAV | O&M | 2021-04-01 | 183 | 2000000 |  | Hopper
SWG | Gulf Intracoastal Waterway - Corpus Christi to Port Isabel & Channel to Port Harlingen | 21 | NAV | O&M | 2021-05-01 | 214 | 1400000 |  | Pipeline
SWG | Sabine-Neches Waterway - Port Arthur Canal, Junction, Taylors Bayou & Neches River | 21 | NAV | O&M | 2021-06-01 | 245 | 1500000 |  | Pipeline
SWG | Houston Ship Channel - Beacon 78 to Morgans & Barbours Flare | 21 | NAV | O&M | 2021-08-01 | 243 | 2000000 |  | Pipeline
SWG | Matagorda Ship Channel - Entrance Channel | 21 | NAV | O&M | 2021-08-01 | 122 | 800000 |  | Pipeline
SWG | Texas City Ship Channel - Main Channel & Turning Basin | 21 | NAV | O&M | 2021-08-01 | 243 | 1400000 |  | Pipeline
SWG | Freeport Harbor - Jetty Channel and Inside Channel | 21 | NAV | O&M | 2021-09-01 | 61 | 2200000 |  | Hopper
SWG | Brazos Island Harbor - Jetty Channel | 21 | NAV | O&M | 2021-09-01 | 122 | 400000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Caney Creek to Upper Matagorda Bay & MSC Intersection | 21 | NAV | O&M | 2021-09-01 | 212 | 1200000 |  | Pipeline
SWG | Houston Ship Channel - Bayport Flare and Redfish to BCN 78 | 21 | NAV | O&M | 2021-09-01 | 242 | 3000000 |  | Pipeline
SWG | Matagorda Ship Channel - Matagorda Pen. To Point Comfort | 21 | NAV | O&M | 2021-09-01 | 181 | 2200000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Inner Basin to Viola | 22 | NAV | O&M | 2021-10-01 | 212 | 2500000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Inner Basin to Viola & La Quinta Channel | 22 | NAV | O&M | 2021-10-01 | 212 | 2500000 |  | Pipeline
SWG | Galveston Harbor - Inner Harborr Maintenance Dredging | 22 | NAV | O&M | 2022-05-01 | 153 | 2000000 |  | Hopper.Bucket
SWG | Channel to Victoria - Lower Reach | 22 | NAV | O&M | 2022-05-01 | 153 | 750000 |  | Pipeline
SWG | Channel to Victoria - Lower Reach | 22 | NAV | O&M | 2022-05-01 | 153 | 600000 |  | Pipeline
SWG | GIWW - Across Aransas Bay & Intersection of Matagorda Ship Channel | 22 | NAV | O&M | 2022-05-01 | 153 | 1000000 |  | Pipeline
SWG | GIWW - Corpus Christi to Port Isabel | 22 | NAV | O&M | 2022-05-01 | 214 | 1500000 |  | Pipeline
SWG | Brazos Island Harbor - Main Channel | 22 | NAV | O&M | 2022-06-01 | 182 | 2000000 |  | Pipeline
SWG | Chocolate Bayou - Maintenance Dredging | 22 | NAV | O&M | 2022-06-01 | 214 | 700000 |  | Pipeline
SWG | Gulf Intracoastal Waterway - Freeport to Caney Creek | 22 | NAV | O&M | 2022-07-01 | 153 | 1400000 |  | Pipeline
SWG | Freeport Harbor - Jetty Channel and Inside Channel | 22 | NAV | O&M | 2022-08-01 | 92 | 2200000 |  | Hopper
SWG | Sabine-Neches Waterway - Outer Bar & Bank & Pass Channel | 22 | NAV | O&M | 2022-08-01 | 122 | 2000000 |  | Hopper
SWG | Sabine-Neches Waterway - Port Arthur Canal, Junction, Taylors Bayou | 22 | NAV | O&M | 2022-08-01 | 122 | 2200000 |  | Pipeline
SWG | Brazos Island Harbor - Jetty Channel | 22 | NAV | O&M | 2022-09-01 | 122 | 500000 |  | Hopper
SWG | Houston Ship Channel - Bayport Main Channel and Flare | 22 | NAV | O&M | 2022-09-01 | 242 | 1500000 |  | Pipeline
SWG | Houston Ship Channel - Exxon to Boggy Bayou & Jacintoport | 22 | NAV | O&M | 2022-09-01 | 242 | 1800000 |  | Pipeline
SWG | Corpus Christi Ship Channel - Inner Basin to Viola | 23 | NAV | O&M | 2022-10-01 | 212 | 2500000 |  | Pipeline
SWG | GIWW - Rollover to Causeway and Bolivar Flare | 23 | NAV | O&M | 2022-10-01 | 212 | 800000 |  | Pipeline
Note on G179: McMahon, Joseph W CIV USARMY CENAO (US): At Feeder Ditch

## Pick Lists
Row Status | Job Status | District | FY | Mission | Project Category | Dollar Range | Disposal Types | Dredge Type | Sub-Type | Contract Type | SBA Set Aside
New | Active | LRB | 18 | NAV | O&M | A - 0 - 99,000 | Beach Nourishment | Hopper | Hopper | Converted from IFB to RFP | Unrestricted
In DIS but Updated | Bids>25% of Gov Estimate-converted to RFP | LRC | 19 | FRM | New Work | B - 100,000 - 499,000 | Beach Nourishment and Upland | Bucket | Small 0-3,000 CY | Fair and Reasonable | Small Business
In DIS | Bids>25% of Gov Estimate-resolicit | LRD | 20 |  | Mixed | C - 500,000 - 999,999 | Confined | Pipeline | Medium 3,000-6,000 CY | Hired Labor | Government
| Bids>25%of Gov Estimate-withdrawn | LRE | 21 |  |  | D - 1,000,000 - 4,999,999 | Mixed | Combo | Large 6,000+ | Indef Del Indef Quan (IDIQ) | 8a Set Aside
| Claim on Payment Pending | LRH | 22 |  |  | E - 5,000,000 and above | Open and Upland | Pipeline.Bucket | Unknown | Multiple Award Task Order | Emerging Small Bus. Set Aside
| Completed | LRL | 23 |  |  | Undefined range | Overboard and Open Water | Pipeline.Hopper |  | Negotiated | Hubzone
| Hold-Awaiting Funding | LRN |  |  |  |  | Undefined | Hopper.Bucket | Bucket | Request for Proposal (RFP) | Service Disabled/Veteran Owned
| Hold-Awaiting Permi(s) | LRP |  |  |  |  | Underwater Confined | Dustpan | 0-10 CY | Sole Source | Unknown
| Hold-Protest on Bid | MVD |  |  |  |  | Upland |  | 10-20 CY |  | Veteran Owned
| Hold-Miscellaneous Reason | MVK |  |  |  |  | Wetland Nourishment or Creation |  | 20+ CY |  | Woman Owned
| Moved to Another FY | MVN | [6 empty] | Unknown
| No Bids Received | MVP
| Open by Amendment | MVR | [6 empty] | Pipeline
| Proposed-greater than 80% chance | MVS | [6 empty] | 0-16"
| Terminated | NAD | [6 empty] | 16-24"
| Withdrawn | NAN | [6 empty] | 24"+
| Undefined | NAO | [6 empty] | Ocean Certified
|  | NWD | [6 empty] | Unknown
NWP
|  | NWS | [6 empty] | Combo
|  | NWW | [6 empty] | All
SAD
|  | SAJ | [6 empty] | Pipeline.Bucket
|  | SAM | [6 empty] | 0-16"
|  | SAS | [6 empty] | 16-24"
|  | SAW | [6 empty] | 24"+
|  | SPD | [6 empty] | Ocean Certified
|  | SPK | [6 empty] | Unknown
SWD
|  | SWG | [6 empty] | Pipeline.Hopper
|  | SWL | [6 empty] | 0-16"
|  | SWT | [6 empty] | 16-24"
24"+
Ocean Certified
Unknown
Hopper.Bucket
Small 0-3,000 CY
Medium 3,000-6,000 CY
Large 6,000+
Unknown
Dustpan
0-16"
16-24"
24" +
Unknown